## Test Upload
Orchestrator Number | Bot ID | SRCR # | Service Now Ticket | Process Name | Description | Type | Request Date | Discovery Start Date | Ready for Scrum Date | Requester | Process Owner | Product Manager | Dev Team | Current Status | Funding | Country | Initiative | Domain | Product Area | Business Prioritization | # of transactions per week | Associate avg time (mins) | ROI | IA Prioritization | FTE Savings | Saving Type | Est. Budget | T shirt size | Est. Build Time | Actual Budget | Actual Build Time | # of Bots | Schedules | Peak Times | Success Rate | Tenant Name | Comments | Name | Last Updated | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW |  | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW
Process ID | Robot ID | SRCR # | Record ID | Process Name | Description | Development Type | Date Created | Discovery Start Date | Ready for Scrum Date | Requester | Process Owner | PM Assigned | Scrum Team | Status | Funding | Country |  | Domain | Product Area |  | Number of Transactions per Frequency (estimate) | Average Time per Transaction (mins) | ROI (estimate) |  | Number of Full Time Assocates |  | Budget (estimate) | Complexity |  | Budget (actual) | [5 empty] | Tenant |  |  |  | Service Type | Request Status | Development Start Date | Go Live Date | Decommissioned Date | Process Owner Email | Process Frequency | Cost of One Full Time Associate | Expense Reduction | Expense Reduction Dollar Amount | Expense Reduction Frequency | Headcount Reduction | Headcount Reduction Amount (estimate) | Revenue Generated | Revenue Generated Dollar Amount | Revenue Generated Frequency | Cost Avoidance | Cost Avoidance Dollar Amount | Hours Saved | Error Reduction | Volume | Compliance | Associate/Customer Experience | Expanded Services | Cost Center Area Name | Cost Center Number | Dollar Amount Charged | Production Machine(s) | Applications | SOX | CRQ Number | Design Review Approved | Design Review Approved By | Code Review Approved | Code Review Approved By | Business Approval | Business Approval By
3408 | svc_dag0011 | 41851846 | REC000001 | Open Payables Preparing wire requests | Preparing wire requests and pulling invoices for open payables. | New | 2018-06-15 |  |  | Tracy Spicer | Kristyn Baker | Matthew Hill | Thunder Bots | Production | Yes | US | GenPact | Accounts Payable | General Ledger | 4 | 15 | 60 | 2867 |  |  | Hours Saved |  | Large | 12.5 weeks |  | TBD | 1 | TBD |  |  |  |  | 3408 Open Payables Preparing wire requests Accounts Payable General Ledger | 2019-05-21 | COE Team Discovery | Completed |  |  |  |  | Weekly |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | [5 empty] | No
2510 |  | 42097447 | REC000002 | AOP: Unemployment | Data pull from Store Level Wage Salary, State Forecast, AND Last Year’s Unemployment Taxes are used to calculate/forecast the unemployment tax expense calculations for current year. Calculations are added to the overall AOP (Annual Operation Plan) | New | 2019-03-01 | 2019-03-26 | 2019-04-12 | Josh Walker | Erik Owczarczak | Charlene Walker | Big Bots | UAT | No | US | AOP | Finance | Corporate FP & A | 1 |  | 120 | null | 1 |  | Hours Saved |  | X-Small | 2 weeks |  | 2 weeks | 1 | null | null | null |  |  | 2510 AOP: Unemployment Finance Corporate FP & A | 2019-05-21 | COE Team Discovery | Completed |  |  |  |  | Quarterly |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 1 | 1 | 0 | 0 | 1 | 0 |  |  |  |  | Essbase, Excel | No

## Charlene Upload
Process ID | Bot ID | SRCR # | RECORD # | Process Name | Description | Type | Request Date | Discovery Start Date | Ready for Scrum Date | Requester | Process Owner | Product Manager | Scrum Team | Current Status | Funding | Country | Initiative | Domain | Product Area | # of transactions | Associate avg time (mins) | ROI | Number of FTE | Est. Budget | T shirt size | Actual Budget | Tenant Name | Comments | Name | Last Updated Date | Service Type | Request Status | Development Start Date | Go Live Date | Decommissioned Date | Process Owner Email | Process Frequency | Cost of One Full Time Associate | Expense Reduction | Expense Reduction Dollar Amount | Expense Reduction Frequency | Headcount Reduction | Headcount Reduction Amount (estimate) | Revenue Generated | Revenue Generated Dollar Amount | Revenue Generated Frequency | Cost Avoidance | Cost Avoidance Dollar Amount | Hours Saved | Error Reduction | Volume | Compliance | Associate/Customer Experience | Expanded Services | Cost Center Area Name | Cost Center Number | Dollar Amount Charged | Production Machine(s) | Applications | SOX | CRQ Number | Design Review Approved | Design Review Approved By | Code Review Approved | Code Review Approved By | Business Approval | Business Approval By
1031 |  |  | REC000033 | Shoes GR/IR Process | Match and count receivings with invoice to reduce overpayment and quantity count | New | 2019-04-18 | 2019-04-18 |  | Louie Knapp | Sarah Moreton | Charlene Walker |  | Discovery | No | US | Merger | GBS | M&A |  | 5 |  |  |  | Large |  |  |  |  | 2019-07-24 | COE Team Discovery | Completed |  |  |  |  | Daily |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 1 | 1 | 1 | 0 | 1 | 0
2510 | Attended | 42097447 | REC000082 | AOP: Unemployment | Data pull from Store Level Wage Salary, State Forecast, AND Last Year’s Unemployment Taxes are used to calculate/forecast the unemployment tax expense calculations for current year. Calculations are added to the overall AOP (Annual Operation Plan) | New | 2019-03-01 | 2019-03-26 | 2019-04-12 | Josh Walker | Erik Owczarczak | Charlene Walker | Big Bots | UAT | No | US | AOP | Finance | Corporate FP & A | 15 | 120 |  |  |  | X-Small |  |  |  | 2510 AOP: Unemployment Finance Corporate FP & A | 2019-07-24 | COE Team Discovery | Completed | 2019-04-15 |  |  | Erick.Owczarczak@walmart.com | Quarterly |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 1 | 1 | 0 | 0 | 1 | 0 |  |  |  |  | Essbase, Excel, Shared Drive | No |  | 1 |  | 0 |  | Yes | Erick Owczarczak
2511 | Attended | 41960127 | REC000083 | AOP: Store Manager Salary | Store Manager Salary is a process that deals with the forecasting and calculation of head count and daily pay rates for all store managers in US | New | 2019-03-01 | 2019-03-01 | 2019-03-05 | Josh Walker | Keith Clarke | Charlene Walker | Fuzzy Bots | UAT | No | US | AOP | Finance | Corporate FP & A | 15 | 720 |  |  |  | Large |  |  | 07/15: In UAT; process is run Qtrly - expected run first week of August (Keith Clarke) | 2511 AOP: Store Manager Salary Finance Corporate FP & A | 2019-07-24 | COE Team Discovery | Completed | 2019-03-11 |  |  | Keith.Clarke@walmart.com | Annually |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 1 | 1 | 0 | 0 | 1 | 0 |  |  |  |  | Essbase, Excel, Shared Drive, SharePoint | No |  | 1 |  | 0 |  | Yes | Keith Clarke
2512 | Attended | 42097447 | REC000084 | AOP: IMU | Data pull from Essbase database of Net Sales, Sales, and Rates to calculate current fiscal year Rates Plan for stores and Initial Markup plan by portfolio, so that Finance & Strategy Manager can review and make needed adjustments to be add to the overall AOP (Annual Operation Plan)/Budget. These calculations happen twice a year (November: to capture 1st quarter AND February to capture Qtrs 2,3 & 4) | New | 2019-03-01 | 2019-05-09 | 2019-06-04 | Josh Walker | Chris Graves | Charlene Walker | Big Bots | Development | No | US | AOP | Finance | Corporate FP & A | 15 | 480 |  |  |  | Large |  |  |  |  | 2019-07-24 | COE Team Discovery | Completed | 2019-06-10 |  |  | Jackson.Burnside@walmart.com | Quarterly |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 1 | 1 | 0 | 0 | 1 | 0 |  |  |  |  | Essbase, Excel, Shared Drive | No |  | 1 |  | 0 |  | Yes | Chris Graves
2513 | svc_daf0001 | 42276894 | REC000085 | AOP: Tech M&R | Technology Finance Team track actual spend via tracking vendor invoices that lead to store and club analysis. This analysis is done to determine correct allocation charges. At the end of every month allocation charges are done back to the right stores and the forecast planning is aligned to the overall AOP (Annual Operation Plan/Budget). | New | 2019-03-14 | 2019-04-09 | 2019-04-26 | Josh Walker | Douglas Coffed | Charlene Walker | Big Bots | Development | No | US | AOP | Finance | Corporate FP & A | 15 | 720 |  |  |  | Medium |  |  | 07/23: In Development; Demo scheduled on 7/24 w/business | 2513 AOP: Tech M&R Finance Corporate FP & A | 2019-07-24 | COE Team Discovery | Completed | 2019-06-04 |  |  | James.Coffey@walmart.com | Weekly |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 1 | 1 | 0 | 0 | 1 | 0 |  |  |  |  | Outlook, Excel, database, Shared Drive | No |  | 1 |  | 0 |  | Yes | James Coffey
2514 | Attended | 42342798 | REC000086 | AOP: Bank Service Charges | Treasury team monthly needs to capture the dollar amount to be paid to banks for the money deposited in the stores. The associate generates the invoices files and sends to the banks via e-mail for review and then shares with Treasury manager and director for approval. Once approved, the invoices are sent for to AP through BPM. | New | 2019-03-14 | 2019-04-09 | 2019-04-23 | Josh Walker | David Shelly | Charlene Walker | Fuzzy Bots | Development | No | US | AOP | Finance | Corporate FP & A | 5 | 360 |  |  |  | Medium |  |  |  | 2514 AOP: Bank Service Charges Finance Corporate FP & A | 2019-07-24 | COE Team Discovery | Completed | 2019-06-04 |  |  | Caryn.Moutrey@walmart.com | Weekly |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 1 | 1 | 0 | 0 | 1 | 0 |  |  |  |  | Outlook, Excel, Shared Drive, BPM | No |  | 1 |  | 0 |  | Yes | Caryn Moutrey
2516 | Attended |  | REC000088 | AOP: Margin: Sales Mix | The Finance Data & Strategy Team calculates the percentage sales mix by portfolio. A Sales Mix is a forecasting model used to predict the percent of total sales coming from each department by month per store. The team uses this model to support the calculation of the IMU (Initial Mark Up) by product. | New | 2019-03-14 | 2019-06-11 | 2019-06-18 | Josh Walker | Chris Graves | Charlene Walker | ThunderBots | Development | No | US | AOP | Finance | Corporate FP & A | 15 | 360 |  |  |  | Medium |  |  |  |  | 2019-07-24 | COE Team Discovery | Completed | 2019-06-24 |  |  | Lindsey.Keeling@walmart.com | Quarterly |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 1 | 1 | 0 | 0 | 1 | 0 |  |  |  |  | Essbase, Excel, Shared Drive | No |  | 1 |  | 0 |  | Yes | Lindsey Keeling
2517 | svc_daf0002 | 42241727 | REC000089 | AOP: RE Expenses | Forecasting process for Remodel expenses on stores. The RE Finance team monthly query Quickbase and SAP to feed a model in excel which automatically calculates the expenses forecast for the stores. | New | 2019-03-14 | 2019-04-24 | 2019-05-14 | Josh Walker | Jason Porter | Charlene Walker | ThunderBots | UAT | No | US | AOP | Finance | Corporate FP & A | 5 | 180 |  |  |  | Small |  |  | 05/17: Current Status: Ready for Scrum: Will update # of Bots AND Actual Build Time when Team has completed | 2517 AOP: RE Expenses Finance Corporate FP & A | 2019-07-24 | COE Team Discovery | Completed | 2019-06-17 |  |  | Jacqueline.Diaz@walmart.com | Weekly |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 1 | 1 | 0 | 0 | 1 | 0 |  |  |  |  | SAP, Excel, Shared Drive | No |  | 1 |  | 0 |  | Yes | Jacqueline Diaz
2518 |  |  | REC000090 | AOP: Baseline Merch & Service Sales | Store Plans are sent to Market Managers and District Manager to set store plan goals for the new year. Helps in planning and hitting targets set | New | 2019-06-07 | 2019-07-15 | 2019-07-18 | Josh Walker | Lindsey Keeling | Charlene Walker | Big Bots | Development | No | US | AOP | Finance | Corporate FP & A | 50 | 10 |  |  |  | Small |  |  |  |  | 2019-07-24 | COE Team Discovery | Completed | 2019-07-22 |  |  | Lindsey.Keeling@walmart.com | Quarterly |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 1 | 1 | 0 | 0 | 1 | 0 |  |  |  |  | Excel, Shared Drive | No |  | 1 |  | 0 |  | Yes | Lindsey Keeling
2519 | Attended | 42097447 | REC000091 | AOP: Mgmt Fee (Spread by Sq Ft) | Data pull from Essbase database of individual store square footage, rates and allocated dollars from Central Reporting Team to allocate correct dollar amounts by store to offset overhead. The Finance & Strategy Manager can review and make needed adjustments to be add to the overall AOP (Annual Operation Plan)/Budget. These calculations quarterly | New | 2019-04-23 | 2019-05-08 | 2019-05-14 | Josh Walker | Lindsey Keeling | Charlene Walker | Big Bots | UAT | No | US | AOP | Finance | Corporate FP & A | 15 | 120 |  |  |  | X-Small |  |  | 05/17: Current Status: Ready for Scrum: Will update # of Bots AND Actual Build Time when Team has completed | 2519 AOP: Mgmt Fee (Spread by Sq Ft) Finance Corporate FP & A | 2019-07-24 | COE Team Discovery | Completed | 2019-05-04 |  |  | Jackson.Burnside@walmart.com | Quarterly |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 1 | 1 | 0 | 0 | 1 | 0 |  |  |  |  | Essbase, Excel, Shared Drive | No |  | 1 |  | 0 |  | Yes | Lindsey Keeling
2520 |  |  | REC000092 | AOP: Register Cash Short/Long | Register Cash Short/Long is the forecast of shrink and the allocation of funding to cover based on format | New | 2019-04-24 | 2019-06-14 | 2019-06-24 | Josh Walker | Lindsey Keeling | Charlene Walker | Fuzzy Bots | Development | No | US | AOP | Finance | Corporate FP & A | 15 | 90 |  |  |  | Small |  |  |  |  | 2019-07-24 | COE Team Discovery | Completed | 2019-07-01 |  |  | Tiffani.BrownBrent@walmart.com | Quarterly |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 1 | 1 | 0 | 0 | 1 | 0 |  |  |  |  | Essbase, Excel, Shared Drive | No |  | 1 |  | 0 |  | Yes | Tiffani Brown - Brent
2521 | Attended | 42097447 | REC000093 | AOP - FICA | Data pull from Store Level Wage Salary, Salary AND Last Year’s FICA Taxes are used to calculate/forecast the FICA tax expense calculations for current year. Calculations are added to the overall AOP (Annual Operation Plan) | New | 2019-03-13 | 2019-03-26 | 2019-04-02 | Josh Walker | Erik Owczarczak | Charlene Walker | Big Bots | UAT | No | US | AOP | Finance | Corporate FP & A | 15 | 120 |  |  |  | X-Small |  |  |  | 2521 AOP - FICA Finance Corporate FP & A | 2019-07-24 | COE Team Discovery | Completed | 2019-04-29 |  |  | Erick.Owczarczak@walmart.com | Quarterly |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 1 | 1 | 0 | 0 | 1 | 0 |  |  |  |  | Essbase, Excel, Shared Drive | No |  | 1 |  | 0 |  | Yes | Erick Owczarczak
2522 |  |  | REC000094 | AOP: Supplies | Pull data for historical KPI, attributes and historical spend so they can all be used by an existing model which will support the budgeting of supplies for the stores | New | 2019-05-14 | 2019-06-24 | 2019-07-08 | Josh Walker | Peggy Berger/Neil Limberg | Charlene Walker | ThunderBots | Development | No | US | AOP | Finance | Corporate FP & A | 20 | 120 |  |  |  | Medium |  |  |  |  | 2019-07-24 | COE Team Discovery | Completed | 2019-07-15 |  |  | Peggy.Berger@walmart.com | Quarterly |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 1 | 1 | 0 | 0 | 1 | 0 |  |  |  |  | Essbase, Excel, Shared Drive | No |  | 1 |  | 0 |  | Yes | Peggy Berger
3000 |  | 41367499 | REC000095 | LIFT: CLT Credit Memos | Platform migration from Assist Edge to UIPath | New | 2018-01-01 | 2018-08-06 | 2018-08-20 | GBS IA Team | Sriram Balu | Charlene Walker | LIFT | Production | No | US | LIFT | Finance | AP | 60000 | 10 |  |  |  | Medium |  |  |  | 3000 US LIFT: CLT Credit Memos Finance AP | 2019-07-24 | COE Team Discovery | Completed | 2018-10-01 |  |  | Sriram.Balu@walmart.com | Daily |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 1 | 1 | 1 | 0 | 1 | 0 |  |  |  |  | WATT, SMART | No |  | 1 |  | 1 |  | Yes | Sriram Balu
3001 |  | 41367499 | REC000096 | LIFT: CLT Bottle Deposits | Platform migration from Assist Edge to UIPath | New | 2018-01-01 | 2018-11-12 | 2018-11-30 | GBS IA Team | Sriram Balu | Charlene Walker | LIFT | Production | No | US | LIFT | Finance | AP | 72000 | 10 |  |  |  | Medium |  |  |  | 3001 US LIFT: CLT Bottle Deposits Finance AP | 2019-07-24 | COE Team Discovery | Completed | 2018-11-26 |  |  | Sriram.Balu@walmart.com | Daily |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 1 | 1 | 1 | 0 | 1 | 0 |  |  |  |  | WATT,SMART,DB2 | No |  | 1 |  | 1 |  | Yes | Sriram Balu
3002 |  | 41367499 | REC000097 | LIFT: CLT K&F | Platform migration from Assist Edge to UIPath | New | 2018-01-01 | 2018-11-12 | 2018-11-30 | GBS IA Team | Sriram Balu | Charlene Walker | LIFT | Production | No | US | LIFT | Finance | AP | 133,00 | 2 |  |  |  | Medium |  |  |  | 3002 US LIFT: CLT K&F Finance AP | 2019-07-24 | COE Team Discovery | Completed | 2018-11-26 |  |  | Sriram.Balu@walmart.com | Daily |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 1 | 1 | 1 | 0 | 1 | 0 |  |  |  |  | WATT,SMART,DB2 | No |  | 1 |  | 1 |  | Yes | Sriram Balu
3003 |  | 41367499 | REC000098 | LIFT: CLT EDI (US) | Platform migration from Assist Edge to UIPath | New | 2018-01-01 | 2018-11-12 | 2018-11-30 | GBS IA Team | Sriram Balu | Charlene Walker | LIFT | Production | No | US | LIFT | Finance | AP | 72000 | 10 |  |  |  | Medium |  |  |  | 3003 LIFT: CLT EDI (US) Finance AP | 2019-07-24 | COE Team Discovery | Completed | 2018-11-26 |  |  | Sriram.Balu@walmart.com | Daily |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 1 | 1 | 1 | 0 | 1 | 0 |  |  |  |  | WATT,SMART,DB2 | No |  | 1 |  | 1 |  | Yes | Sriram Balu
3004 |  | 41367499 | REC000099 | LIFT: CLT EDI (CA) | Platform migration from Assist Edge to UIPath | New | 2018-01-01 | 2018-11-12 | 2018-11-30 | GBS IA Team | Sriram Balu | Charlene Walker | LIFT | Production | No | CA | LIFT | Finance | AP | 72000 | 10 |  |  |  | Medium |  |  |  | 3004 LIFT: CLT EDI (CA) Finance AP | 2019-07-24 | COE Team Discovery | Completed | 2018-11-26 |  |  | Sriram.Balu@walmart.com | Daily |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 1 | 1 | 1 | 0 | 1 | 0 |  |  |  |  | WATT,SMART,DB2 | No |  | 1 |  | 1 |  | Yes | Sriram Balu
3005 |  | 41367499 | REC000100 | LIFT: CLT McKesson | Platform migration from Assist Edge to UIPath | New | 2018-01-01 | 2018-11-19 | 2018-12-04 | GBS IA Team | Sriram Balu | Charlene Walker | LIFT | Production | No | US | LIFT | Finance | AP | 72000 | 10 |  |  |  | Medium |  |  |  | 3005 US LIFT: CLT McKesson Finance AP | 2019-07-24 | COE Team Discovery | Completed | 2018-12-10 |  |  | Sriram.Balu@walmart.com | Daily |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 1 | 1 | 1 | 0 | 1 | 0 |  |  |  |  | WATT,SMART,DB2 | No |  | 1 |  | 1 |  | Yes | Sriram Balu
3006 |  | 41367499 | REC000101 | LIFT: CLT Cardinal | Platform migration from Assist Edge to UIPath | New | 2018-01-01 | 2018-11-19 | 2018-12-04 | GBS IA Team | Sriram Balu | Charlene Walker | LIFT | Production | No | US | LIFT | Finance | AP | 72000 | 10 |  |  |  | Medium |  |  |  | 3006 US LIFT: CLT Cardinal Finance AP | 2019-07-24 | COE Team Discovery | Completed | 2018-12-10 |  |  | Sriram.Balu@walmart.com | Daily |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 1 | 1 | 1 | 0 | 1 | 0 |  |  |  |  | WATT,SMART,DB2 | No |  | 1 |  | 1 |  | Yes | Sriram Balu
3007 |  | 41367499 | REC000102 | LIFT: CLT Automatch | Platform migration from Assist Edge to UIPath | New | 2018-01-01 | 2018-11-19 | 2018-12-06 | GBS IA Team | Sriram Balu | Charlene Walker | LIFT | Production | No | US | LIFT | Finance | AP | 72000 | 10 |  |  |  | Medium |  |  |  | 3007 US LIFT: CLT Automatch Finance AP | 2019-07-24 | COE Team Discovery | Completed | 2018-12-10 |  |  | Sriram.Balu@walmart.com | Daily |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 1 | 1 | 1 | 0 | 1 | 0 |  |  |  |  | WATT,SMART,DB2 | No |  | 1 |  | 1 |  | Yes | Sriram Balu
3008 |  | 41367499 | REC000103 | CLT Receipt Not Found |  | New | 2018-01-01 | 2018-09-03 | 2018-08-20 | GBS IA Team | Sriram Balu | Charlene Walker | LIFT | Production | No | US | LIFT | Finance | AP | 2000 | 2 |  |  |  | Medium |  |  |  | 3008 US CLT Receipt Not Found Finance AP | 2019-07-24 | COE Team Discovery | Completed | 2018-10-08 |  |  | Sriram.Balu@walmart.com | Daily |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 1 | 1 | 1 | 0 | 1 | 0 |  |  |  |  | WATT,SMART,DB2 | No |  | 1 |  | 1 |  | Yes | Sriram Balu
3009 |  | 41367499 | REC000104 | LIFT: CLT Optical | Platform migration from Assist Edge to UIPath | New | 2018-01-01 | 2018-11-19 | 2018-12-01 | GBS IA Team | Sriram Balu | Charlene Walker | LIFT | Production | No | US | LIFT | Finance | AP | 80000 | 2 |  |  |  | Medium |  |  |  | 3009 US LIFT: CLT Optical Finance AP | 2019-07-24 | COE Team Discovery | Completed | 2018-12-17 |  |  | Sriram.Balu@walmart.com | Daily |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 1 | 1 | 1 | 0 | 1 | 0 |  |  |  |  | WATT,SMART,DB2 | No |  | 1 |  | 1 |  | Yes | Sriram Balu
3010 |  | 41367499 | REC000105 | LIFT: CLT Alcohol | Platform migration from Assist Edge to UIPath | New | 2018-01-01 | 2018-11-19 | 2018-12-01 | GBS IA Team | Sriram Balu | Charlene Walker | LIFT | Production | No | US | LIFT | Finance | AP | 80000 | 2 |  |  |  | Medium |  |  |  | 3010 US LIFT: CLT Alcohol Finance AP | 2019-07-24 | COE Team Discovery | Completed | 2018-12-17 |  |  | Sriram.Balu@walmart.com | Daily |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 1 | 1 | 1 | 0 | 1 | 0 |  |  |  |  | WATT,SMART,DB2 | No |  | 1 |  | 1 |  | Yes | Sriram Balu
3011 |  | 41367499 | REC000106 | LIFT: CLT K&F | Platform migration from Assist Edge to UIPath | New | 2018-01-01 | 2018-11-19 | 2018-12-01 | GBS IA Team | Sriram Balu | Charlene Walker | LIFT | Production | No | US | LIFT | Finance | AP | 80000 | 2 |  |  |  | Medium |  |  |  | 3011 US LIFT: CLT K&F Finance AP | 2019-07-24 | COE Team Discovery | Completed | 2018-12-17 |  |  | Sriram.Balu@walmart.com | Daily |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 1 | 1 | 1 | 0 | 1 | 0 |  |  |  |  | WATT,SMART,DB2 | No |  | 1 |  | 1 |  | Yes | Sriram Balu
3012 |  | 41367499 | REC000107 | LIFT: CLT McKesson | Platform migration from Assist Edge to UIPath | New | 2018-01-01 | 2018-11-19 | 2018-12-01 | GBS IA Team | Sriram Balu | Charlene Walker | LIFT | Production | No | US | LIFT | Finance | AP | 80000 | 2 |  |  |  | Medium |  |  |  | 3012 US LIFT: CLT McKesson Finance AP | 2019-07-24 | COE Team Discovery | Completed | 2018-12-17 |  |  | Sriram.Balu@walmart.com | Daily |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 1 | 1 | 1 | 0 | 1 | 0 |  |  |  |  | WATT,SMART,DB2 | No |  | 1 |  | 1 |  | Yes | Sriram Balu
3013 |  | 41367499 | REC000108 | LIFT: CLT Non Authorized | Platform migration from Assist Edge to UIPath | New | 2018-01-01 | 2018-11-19 | 2018-12-01 | GBS IA Team | Sriram Balu | Charlene Walker | LIFT | Production | No | US | LIFT | Finance | AP | 80000 | 2 |  |  |  | Medium |  |  |  | 3013 US LIFT: CLT Non Authorized Finance AP | 2019-07-24 | COE Team Discovery | Completed | 2018-12-17 |  |  | Sriram.Balu@walmart.com | Daily |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 1 | 1 | 1 | 0 | 1 | 0 |  |  |  |  | WATT,SMART,DB2 | No
3014 | svc_daa0025 | 36136997 | REC000109 | Mark Up/Mark Down (US) | RA to process all exceptions items ; price change exceptions that reached $$ and quantity threshold that are suspended for further action | New | 2018-03-29 | 2018-03-19 | 2018-04-13 | AP Digital Factory | Debra Luedtke | Charlene Walker | AP Digital Factory | Production | Yes | US | AP - Digital Factory | Finance | AP | 18421.6 | 2 | 67959.02 | 19 |  | Medium |  |  | Kick-off held April 11th -- Development started mid-May | 3014 US Mark Up/Mark Down (US) Finance AP | 2019-07-24 | COE Team Discovery | Completed | 2018-04-16 |  |  | Debra.Luedtke@walmart.com | Daily |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 1 | 1 | 1 | 0 | 1 | 0 |  |  |  |  | SMART, BPM, WATT | No |  | 1 |  | 1 |  | 1 | Debra Luedtke
3015 | svc_daa0026 | 36136997 | REC000110 | Mark Up/Mark Down (CA) | RA to process all exceptions items ; price change exceptions that reached $$ and quantity threshold that are suspended for further action | New | 2018-03-29 | 2018-03-19 | 2018-04-13 | AP Digital Factory | Debra Luedtke | Charlene Walker | AP Digital Factory | Production | Yes | CA | AP - Digital Factory | Finance | AP | 19821.6 | 2 | 63159.07 | 20 |  | Medium |  |  | Kick-off held April 11th -- Development started mid-May | 3015 CA Mark Up/Mark Down (CA) Finance AP | 2019-07-24 | COE Team Discovery | Completed | 2018-04-16 |  |  | Debra.Luedtke@walmart.com | Daily |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 1 | 1 | 1 | 0 | 1 | 0 |  |  |  |  | SMART, BPM, WATT | No |  | 1 |  | 1 |  | 1 | Debra Luedtke
3016 | svc_daa0023 | 36116680 | REC000111 | MTR (US) | MTR Reconciliation End to End Process (Charged not Received, Shortage/Overage, Retail Correction, BPM, WATT ) | New | 2018-03-29 | 2018-03-19 | 2018-04-04 | AP Digital Factory | Debra Luedtke | Charlene Walker | AP Digital Factory | Production | Yes | US | AP - Digital Factory | Finance | AP | 9940.8 | 5 | 85205.91 | 25 |  | Medium |  |  | Kick-off held April 11th -- Development started mid-May | 3016 US MTR (US) Finance AP | 2019-07-24 | COE Team Discovery | Completed | 2018-04-09 |  |  | Debra.Luedtke@walmart.com | Daily |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 1 | 0 | 1 | 0 |  |  |  |  | SMART, BPM, WATT | No |  | 1 |  | 1 |  | 1 | Debra Luedtke
3017 | svc_daa0024 | 36116680 | REC000112 | MTR (CA) | MTR Reconciliation End to End Process (Charged not Received, Shortage/Overage, Retail Correction, BPM, WATT) | New | 2018-03-29 | 2018-03-19 | 2018-04-04 | AP Digital Factory | Debra Luedtke | Charlene Walker | AP Digital Factory | Production | Yes | CA | AP - Digital Factory | Finance | AP | 1043.2 | 5 | 8941.61 | 3 |  | Medium |  |  | Kick-off held April 11th -- Development started mid-May | 3017 CA MTR (CA) Finance AP | 2019-07-24 | COE Team Discovery | Completed | 2018-04-09 |  |  | Debra.Luedtke@walmart.com | Daily |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 1 | 0 | 1 | 0 |  |  |  |  | SMART, BPM, WATT | No |  | 1 |  | 1 |  | 1 | Debra Luedtke
3018 | svc_daa0021 | 36105933 | REC000113 | Transmittals (US) | Transmittals End to End Process (Error Transmittals, Not Finalized Transmittals update, BPM, WATT) | New | 2018-03-29 | 2018-03-19 | 2018-04-18 | AP Digital Factory | Debra Luedtke | Charlene Walker | AP Digital Factory | Production | Yes | US | AP - Digital Factory | Finance | AP | 2989.6 | 5 | 25624.86 | 7 |  | Medium |  |  | Kick-off held April 11th -- Development started end of May | 3018 US Transmittals (US) Finance AP | 2019-07-24 | COE Team Discovery | Completed | 2018-04-09 |  |  | Debra.Luedtke@walmart.com | Daily |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 1 | 0 | 1 | 0 |  |  |  |  | SMART, BPM, WATT | No |  | 1 |  | 1 |  | 1 | Debra Luedtke
3019 | svc_daa0022 | 36105933 | REC000114 | Transmittals (CA) | Transmittals End to End Process (Error Transmittals, Not Finalized Transmittals update, BPM,WATT) | New | 2018-03-29 | 2018-03-23 | 2018-04-18 | AP Digital Factory | Debra Luedtke | Charlene Walker | AP Digital Factory | Production | Yes | CA | AP - Digital Factory | Finance | AP | 2713.2 | 5 | 23255.74 | 7 |  | Medium |  |  | Kick-off held April 11th -- Development started end of May | 3019 CA Transmittals (CA) Finance AP | 2019-07-24 | COE Team Discovery | Completed | 2018-03-26 |  |  | Debra.Luedtke@walmart.com | Daily |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 1 | 0 | 1 | 0 |  |  |  |  | SMART, BPM, WATT | No |  | 1 |  | 1 |  | 1 | Debra Luedtke
3020 | svc_daa0027 | 36140475 | REC000115 | McKesson - High Retail Corrections Audit(US) | Matching Threshold changed from $15 to $20 or $30. RA audit and High Retail Corrections in SMART | New | 2018-03-29 | 2018-03-23 | 2018-04-30 | AP Digital Factory | Debra Luedtke | Charlene Walker | AP Digital Factory | Production | Yes | US | AP - Digital Factory | Finance | AP | 1463.2 | 12 | 30099.78 | 13 |  | Medium |  |  | Kick-off held April 11th -- Development started first week of June | 3020 US McKesson - High Retail Corrections Audit(US) Finance AP | 2019-07-24 | COE Team Discovery | Completed | 2018-03-26 |  |  | Debra.Luedtke@walmart.com | Daily |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 1 | 0 | 1 | 0 |  |  |  |  | SMART, BPM, WATT | No |  | 1 |  | 1 |  | 1 | Debra Luedtke
3021 |  |  | REC000116 | GFR (US) | Goods For Resale Exception process - warehouse | New | 2018-11-27 |  | 2018-11-14 | AP Digital Factory | Debra Luedtke | Charlene Walker | AP Digital Factory | Production | No | US | AP - Digital Factory | Finance | AP | [5 empty] | XLarge |  |  |  | 3021 GFR (US) Finance AP | 2019-07-24 | COE Team Discovery | Completed |  |  |  |  | Daily |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 |  |  | 0 | 1 | [6 empty] | No |  | 1
3022 |  |  | REC000117 | Letter of Credit | Letter of Credit Exceptions and Improvements | New | 2018-11-16 |  | 2018-11-14 | AP Digital Factory | Debra Luedtke | Charlene Walker | AP Digital Factory | Production | No | US | AP - Digital Factory | Finance | AP | [5 empty] | XLarge |  |  |  | 3022 Letter of Credit Finance AP | 2019-07-24 | COE Team Discovery | Completed |  |  |  |  | Daily |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 |  |  | 0 | 1 | [6 empty] | No |  | 1
3023 |  |  | REC000118 | Warehouse Disputes (US) | Warehouse Disputes | New | 2018-03-29 |  |  | AP Digital Factory | Debra Luedtke | Charlene Walker | AP Digital Factory | Production | No | CA | AP - Digital Factory | Finance | AP | [5 empty] | TBD |  |  |  | 3023 Warehouse Disputes (US) Finance AP | 2019-07-24 | COE Team Discovery | Completed |  |  |  |  | Daily |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 |  |  | 0 | 1 | [6 empty] | No |  | 1
3024 |  | 41623617 | REC000119 | NOF MUMD (US) | Not of File Mark Up /Mark Down Exceptions | New | 2018-10-23 | 2019-01-30 | 2019-02-04 | Bruce Crow | Rob Grippi | Charlene Walker | LIFT | Production | No | US | LIFT | Finance | AP | 10000 | 2 |  |  |  | Large |  |  |  | 3024 NOF MUMD (US) Finance AP | 2019-07-24 | COE Team Discovery | Completed | 2019-02-18 |  |  | Alexander.Grippi@walmart.com | Daily |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 1 | 0 | 1 | 0 |  |  |  |  | SMART, Teradata | No |  | 1 |  | 1 |  | 1 | Rob Grippi
3025 |  |  | REC000120 | OCR - Update Naming | OCR | New | 2018-11-27 |  |  | AP Digital Factory | Debra Luedtke | Charlene Walker | AP Digital Factory | On Hold - Funding | No | US | AP - Digital Factory | Finance | AP | [9 empty] | 3025 OCR - Update Naming Finance AP | 2019-07-24 | COE Team Discovery | Completed | [6 empty] | 0 |  |  | 0 |  | 0 | [15 empty] | No
3026 |  |  | REC000121 | Import Payment Processing - Ocean Freight | Ocean Freight Payment Processing | New | 2018-11-20 |  | 2018-11-14 | AP Digital Factory | Debra Luedtke | Charlene Walker | AP Digital Factory | Cancelled | No | US | AP - Digital Factory | Finance | AP | [5 empty] | XXLarge |  |  | Business decided to go another route (EDI) 01/16 | 3026 Import Payment Processing - Ocean Freight Finance AP | 2019-07-24 | COE Team Discovery | Completed | [6 empty] | 0 |  |  | 0 |  | 0 | [15 empty] | No
3027 |  |  | REC000122 | GFR (US) - Variable Weight | GFR Variable Weight | New | 2018-11-27 |  |  | AP Digital Factory | Debra Luedtke | Charlene Walker | AP Digital Factory | On Hold - Funding | No | US | AP - Digital Factory | Finance | AP | [5 empty] | Large |  |  |  | 3027 GFR (US) - Variable Weight Finance AP | 2019-07-24 | COE Team Discovery | Completed | [6 empty] | 0 |  |  | 0 |  | 0 | [15 empty] | No
3036 |  |  | REC000133 | SBO Exception Processing Improvements | Invoice Exceptions | New | 2018-11-27 |  |  | AP Digital Factory | Debra Luedtke | Charlene Walker | AP Digital Factory | On Hold - Funding | No | US | AP - Digital Factory | Finance | AP | [5 empty] | TBD |  |  |  | 3036 SBO Exception Processing Improvements Finance AP | 2019-07-24 | COE Team Discovery | Completed | [6 empty] | 0 |  |  | 0 |  | 0 | [15 empty] | No
3201 |  |  | REC000138 | CAM SBO: Transmittals | The results of the work will remove administrative, repetitive tasks from the different formats and centralized locations, driving standardization, automation, compliance and controls for Central America (CAM) 787 stores in total. The work is to leverage the automation code used for MX SBO and apply to CAM in order to automate the exception processing for Open Receivings, Transmittals and MTR processes | New | 2018-07-17 |  |  |  |  | Charlene Walker |  | New | No, but can secure | CAM | Fixed Capacity | Finance | AP | [5 empty] | X-Large |  |  | Like Mexico SBO - need to leverage the existing to do the CAM back office | 3201 CAM SBO: Transmittals Finance AP | 2019-07-24 | COE Team Discovery | Completed | [6 empty] | 0 |  |  | 0 |  | 0 | [15 empty] | No
3600 |  | 41367499 | REC000202 | LIFT: UK Holiday | Platform migration from Assist Edge to UIPath | New | 2018-01-01 | 2018-05-21 | 2018-06-01 | GBS IA Team | Cathy Bell | Charlene Walker | LIFT | Production | No | UK | LIFT | Finance | HR | 25000 | 3 |  |  |  | Medium |  |  |  | 3600 UK LIFT: UK Holiday Finance HR | 2019-07-24 | COE Team Discovery | Completed | 2018-06-18 |  |  | Cathy.Bell@walmart.com | Daily |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 1 | 0 | 1 | 0 |  |  |  |  | C4C,PeopleSoft,SAP | No |  | 1 |  | 1 |  | 1 | Cathy.Bell@walmart.com
3601 |  | 41367499 | REC000203 | LIFT: UK Flexibility | Platform migration from Assist Edge to UIPath | New | 2018-01-01 | 2018-05-21 | 2018-06-01 | GBS IA Team | Cathy Bell | Charlene Walker | LIFT | Production | No | UK | LIFT | HRSS | HR | 25000 | 3 |  |  |  | Medium |  |  |  | 3601 UK LIFT: UK Flexibility HRSS HR | 2019-07-24 | COE Team Discovery | Completed | 2018-06-18 |  |  | Cathy.Bell@walmart.com | Daily |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 1 | 0 | 1 | 0 |  |  |  |  | C4C,PeopleSoft,SAP | No |  | 1 |  | 1 |  | 1 | Cathy.Bell@walmart.com
3602 |  | 41367499 | REC000204 | LIFT: UK Disciplinary | Platform migration from Assist Edge to UIPath | New | 2018-01-01 | 2018-05-21 | 2018-06-01 | GBS IA Team | Cathy Bell | Charlene Walker | LIFT | Production | No | UK | LIFT | HRSS | HR | 25000 | 3 |  |  |  | Medium |  |  |  | 3602 UK LIFT: UK Disciplinary HRSS HR | 2019-07-24 | COE Team Discovery | Completed | 2018-06-18 |  |  | Cathy.Bell@walmart.com | Daily |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 1 | 0 | 1 | 0 |  |  |  |  | C4C,PeopleSoft,SAP | No |  | 1 |  | 1 |  | 1 | Cathy.Bell@walmart.com
3603 |  | 41367499 | REC000205 | LIFT: UK Contract Swipe | Platform migration from Assist Edge to UIPath | New | 2018-01-01 | 2018-05-21 | 2018-06-01 | GBS IA Team | Cathy Bell | Charlene Walker | LIFT | Production | No | UK | LIFT | HRSS | HR | 25000 | 3 |  |  |  | Medium |  |  |  | 3603 UK LIFT: UK Contract Swipe HRSS HR | 2019-07-24 | COE Team Discovery | Completed | 2018-06-18 |  |  | Cathy.Bell@walmart.com | Daily |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 1 | 0 | 1 | 0 |  |  |  |  | C4C,PeopleSoft,SAP | No |  | 1 |  | 1 |  | 1 | Cathy.Bell@walmart.com
3604 |  | 41367499 | REC000206 | LIFT: UK Contract Change | Platform migration from Assist Edge to UIPath | New | 2018-01-01 |  | 2018-06-01 | GBS IA Team | Cathy Bell | Charlene Walker | LIFT | Production | No | UK | LIFT | HRSS | HR |  | 3 |  |  |  | Medium |  |  |  | 3604 LIFT: UK Contract Change HRSS HR | 2019-07-24 | COE Team Discovery | Completed |  |  |  | Cathy.Bell@walmart.com | Daily |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 1 | 0 | 1 | 0 | [5 empty] | No |  | 1 |  | 1
3800 |  | 41367499 | REC000207 | LIFT: Brazil MUMD | Platform migration from Assist Edge to UIPath | New | 2018-01-01 | 2018-05-28 | 2018-06-16 | GBS IA Team | Sriram Balu | Charlene Walker | LIFT | Production | No | BR | LIFT | Finance | AP | 2000 | 2 |  |  |  | Medium |  |  |  | 3800 BR LIFT: Brazil MUMD Finance AP | 2019-07-24 | COE Team Discovery | Completed | 2018-07-02 |  |  | Sriram.Balu@walmart.com | Daily |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 1 | 0 | 1 | 0 |  |  |  |  | SMART,Shared Drive | No |  | 1 |  | 1
3801 |  | 41367499 | REC000208 | LIFT: Brazil Maintenance | Platform migration from Assist Edge to UIPath | New | 2018-01-01 | 2018-03-18 | 2018-04-01 | GBS IA Team | Sriram Balu | Charlene Walker | LIFT | Production | No | BR | LIFT | Finance | AP | 2000 | 2 |  |  |  | Medium |  |  |  | 3801 BR LIFT: Brazil Maintenance Finance AP | 2019-07-24 | COE Team Discovery | Completed | 2018-04-23 |  |  | Sriram.Balu@walmart.com | Daily |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 1 | 0 | 1 | 0 |  |  |  |  | SMART,Shared Drive | No |  | 1 |  | 1
3802 |  | 41367499 | REC000209 | LIFT: Brazil FileReports | Platform migration from Assist Edge to UIPath | New | 2018-01-01 | 2018-02-26 | 2018-03-15 | GBS IA Team | Sriram Balu | Charlene Walker | LIFT | Production | No | BR | LIFT | Finance | AP | 2000 | 2 |  |  |  | Medium |  |  |  | 3802 BR LIFT: Brazil FileReports Finance AP | 2019-07-24 | COE Team Discovery | Completed | 2018-03-12 |  |  | Sriram.Balu@walmart.com | Daily |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 1 | 0 | 1 | 0 |  |  |  |  | SMART,Shared Drive | No |  | 1 |  | 1
3803 |  | 41367499 | REC000210 | LIFT: Brazil Not On File | Platform migration from Assist Edge to UIPath | New | 2018-01-01 | 2018-04-02 | 2018-04-16 | GBS IA Team | Sriram Balu | Charlene Walker | LIFT | Production | No | BR | LIFT | Finance | AP | 2000 | 2 |  |  |  | Medium |  |  |  | 3803 BR LIFT: Brazil Not On File Finance AP | 2019-07-24 | COE Team Discovery | Completed | 2018-04-30 |  |  | Sriram.Balu@walmart.com | Daily |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 1 | 0 | 1 | 0 |  |  |  |  | SMART,Shared Drive | No |  | 1 |  | 1 |  | 1
3804 |  | 41367499 | REC000211 | LIFT: Brazil On Hand Report | Platform migration from Assist Edge to UIPath | New | 2018-01-01 | 2018-05-28 | 2018-06-16 | GBS IA Team | Sriram Balu | Charlene Walker | LIFT | Production | No | BR | LIFT | Finance | AP | 2000 | 2 |  |  |  | Medium |  |  |  | 3804 BR LIFT: Brazil On Hand Report Finance AP | 2019-07-24 | COE Team Discovery | Completed | 2018-06-11 |  |  | Sriram.Balu@walmart.com | Daily |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 1 | 0 | 1 | 0 |  |  |  |  | SMART,Shared Drive | No |  | 1 |  | 1 |  | 1
3805 |  | 41367499 | REC000212 | LIFT: Brazil Recap | Platform migration from Assist Edge to UIPath | New | 2018-04-20 | 2018-04-02 | 2018-04-20 | GBS IA Team | Sriram Balu | Charlene Walker | LIFT | Production | No | BR | LIFT | Finance | AP | 2000 | 2 |  |  |  | Medium |  |  |  | 3805 BR LIFT: Brazil Recap Finance AP | 2019-07-24 | COE Team Discovery | Completed | 2018-09-03 |  |  | Sriram.Balu@walmart.com | Daily |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 1 | 0 | 1 | 0 |  |  |  |  | SMART,Shared Drive | No |  | 1 |  | 1 |  | 1
3806 |  | 41367499 | REC000213 | LIFT: Brazil Daily | Platform migration from Assist Edge to UIPath | New | 2018-01-01 | 2018-02-26 | 2018-03-15 | GBS IA Team | Sriram Balu | Charlene Walker | LIFT | Production | No | BR | LIFT | Finance | AP | 30000 | 2 |  |  |  | Medium |  |  |  | 3806 BR LIFT: Brazil Daily Finance AP | 2019-07-24 | COE Team Discovery | Completed | 2018-03-26 |  |  | Sriram.Balu@walmart.com | Daily |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 1 | 0 | 1 | 0 |  |  |  |  | SMART,GNFe, Voiza, Shared Drive | No |  | 1 |  | 1 |  | 1
3807 |  | 41367499 | REC000214 | LIFT: Brazil Weekly | Platform migration from Assist Edge to UIPath | New | 2018-01-01 | 2018-02-26 | 2018-03-15 | GBS IA Team | Sriram Balu | Charlene Walker | LIFT | Production | No | BR | LIFT | Finance | AP | 30000 | 2 |  |  |  | Medium |  |  |  | 3807 BR LIFT: Brazil Weekly Finance AP | 2019-07-24 | COE Team Discovery | Completed | 2018-03-26 |  |  | Sriram.Balu@walmart.com | Daily |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 1 | 0 | 1 | 0 |  |  |  |  | SMART,GNFe, Voiza, Shared Drive | No |  | 1 |  | 1 |  | 1
3808 |  | 41367499 | REC000215 | LIFT: Brazil Monthly | Platform migration from Assist Edge to UIPath | New | 2018-01-01 | 2018-02-26 | 2018-03-15 | GBS IA Team | Sriram Balu | Charlene Walker | LIFT | Production | No | BR | LIFT | Finance | AP | 30000 | 2 |  |  |  | Medium |  |  |  | 3808 BR LIFT: Brazil Monthly Finance AP | 2019-07-24 | COE Team Discovery | Completed | 2018-03-26 |  |  | Sriram.Balu@walmart.com | Daily |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 1 | 0 | 1 | 0 |  |  |  |  | SMART,GNFe, Voiza, Shared Drive | No |  | 1 |  | 1 |  | 1
3809 |  | 41367499 | REC000216 | LIFT: Brazil Transfer&Return | Platform migration from Assist Edge to UIPath | New | 2018-01-01 | 2018-12-03 | 2018-12-20 | GBS IA Team | Sriram Balu | Charlene Walker | LIFT | Production | No | BR | LIFT | Finance | AP | 30000 | 2 |  |  |  | Medium |  |  |  | 3809 BR LIFT: Brazil Transfer&Return Finance AP | 2019-07-24 | COE Team Discovery | Completed | 2018-12-31 |  |  | Sriram.Balu@walmart.com | Daily |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 1 | 0 | 1 | 0 |  |  |  |  | SMART,GNFe, Voiza, Shared Drive | No |  | 1 |  | 1 |  | 1
3810 |  | 41367499 | REC000217 | LIFT: Brazil Journals | Platform migration from Assist Edge to UIPath | New | 2018-01-01 | 2018-09-24 | 2018-10-12 | GBS IA Team | Sriram Balu | Charlene Walker | LIFT | Production | No | BR | LIFT | Finance | AP | 30000 | 2 |  |  |  | Medium |  |  |  | 3810 BR LIFT: Brazil Journals Finance AP | 2019-07-24 | COE Team Discovery | Completed | 2018-10-22 |  |  | Sriram.Balu@walmart.com | Daily |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 1 | 0 | 1 | 0 |  |  |  |  | SMART,GNFe, Voiza, Shared Drive | No |  | 1 |  | 1 |  | 1
3811 |  | 41367499 | REC000218 | LIFT: Brazil Claims | Platform migration from Assist Edge to UIPath | New | 2018-01-01 | 2018-12-03 | 2018-12-20 | GBS IA Team | Sriram Balu | Charlene Walker | LIFT | Production | No | BR | LIFT | Finance | AP | 25000 | 40 |  |  |  | Medium |  |  |  | 3811 BR LIFT: Brazil Claims Finance AP | 2019-07-24 | COE Team Discovery | Completed | 2018-12-31 |  |  | Sriram.Balu@walmart.com | Daily |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 1 | 0 | 1 | 0 |  |  |  |  | SMART,Shared Drive | No |  | 1 |  | 1 |  | 1
3812 |  | 41367499 | REC000219 | LIFT: Brazil DSD | Platform migration from Assist Edge to UIPath | New | 2018-01-01 | 2018-08-24 | 2018-08-16 | GBS IA Team | Sriram Balu | Charlene Walker | LIFT | Production | No | BR | LIFT | Finance | AP | 75000 | 3 |  |  |  | Medium |  |  |  | 3812 BR LIFT: Brazil DSD Finance AP | 2019-07-24 | COE Team Discovery | Completed | 2018-08-27 |  |  | Sriram.Balu@walmart.com | Daily |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 1 | 0 | 1 | 0 |  |  |  |  | LTM,GNFe, DB2 | No |  | 1 |  | 1 |  | 1
3813 |  | 41367499 | REC000220 | LIFT: Brazil DC Delivery | Platform migration from Assist Edge to UIPath | New | 2018-01-01 | 2018-08-03 | 2018-08-17 | GBS IA Team | Sriram Balu | Charlene Walker | LIFT | Production | No | BR | LIFT | Finance | AP | 75000 | 3 |  |  |  | Medium |  |  |  | 3813 BR LIFT: Brazil DC Delivery Finance AP | 2019-07-24 | COE Team Discovery | Completed | 2018-08-27 |  |  | Sriram.Balu@walmart.com | Daily |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 1 | 0 | 1 | 0 |  |  |  |  | LTM,GNFe, DB3 | No |  | 1 |  | 1 |  | 1
4000 |  | 41367499 | REC000221 | Ticket Flow - Lift | Platform migration from Assist Edge to UIPath | New | 2018-01-01 | 2018-08-24 | 2018-10-12 | GBS IA Team | Sriram Balu | Charlene Walker | LIFT | Production | No | US | LIFT | Finance | AP | 25000 | 2 |  |  |  | Medium |  |  |  | 4000 US Ticket Flow - Lift Finance AP | 2019-07-24 | COE Team Discovery | Completed | 2018-10-22 |  |  | Sriram.Balu@walmart.com | Daily |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 1 | 0 | 1 | 0 |  |  |  |  | WATT | No |  | 1 |  | 1 |  | 1
5400 | Attended | 36239813 | REC000237 | 401K Audit: Participant Data (MVP1: Merrill Lynch) | EY will send a list of associates to conduct an audit on. The team will navigate through different sites to capture screenshots. Then store the screenshots on shared drive for manager to review. This is a quarterly process | New | 2018-11-21 | 2018-05-14 | 2018-05-31 | Margie Molesso | Wendy Byers | Charlene Walker | TR Digital Factory | Production | Yes | US | TR Digital Factory | People | Total Rewards | 100 | 120 |  |  | 9473 | Small | 9473 |  |  | 5400 US 401K Audit: Participant Data (MVP1: Merrill Lynch) People Total Rewards | 2019-07-24 | COE Team Discovery | Completed | 2018-06-04 |  |  | Wendy.Byers@walmart.com | Quarterly |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 1 | 0 | 1 | 0 |  |  |  |  | Merrill Lynch, Shared Drive, HOST | No |  | 1 |  | 1 |  | 1 | Wendy Byers
5401 | svcdah16 | 36239813 | REC000238 | AHWP (MVP1: HOST & OSCAR) | EY will send a list of associates to conduct an ERISA audit on. The associate navigate to HOST and OSCAR to capture the right screens with the associate information. The screenshots are compiled and stored on a shared drive for a manager to review. This is a quarterly process | New | 2018-07-30 | 2018-05-15 | 2018-05-31 | Margie Molesso | Kim Woodard | Charlene Walker | TR Digital Factory | Production | Yes | US | TR Digital Factory | People | Total Rewards | 100 | 240 |  |  | 9473 | Medium | 9473 |  | svcdah16 Access HOST/OSCAR - Done | 5401 US AHWP (MVP1: HOST & OSCAR) People Total Rewards | 2019-07-24 | COE Team Discovery | Completed | 2018-06-05 |  |  | Wendy.Byers@walmart.com | Daily |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 1 | 0 | 1 | 0 |  |  |  |  | HOST, OSCAR, Shared Drive | No |  | 1 |  | 1 |  | 1 | John Doyle
5402 | Attended | 41197917 | REC000239 | 401K Maintenance Rejection File (MVP1: Rejection File) | Process Rejection Files returned by Merrill Lynch | New | 2018-08-06 | 2018-07-30 | 2018-08-12 | Wendy Byers | Wendy Byers | Charlene Walker | TR Digital Factory | Production | Yes | US | TR Digital Factory | People | Total Rewards | 100 | 120 |  |  | 9473 | Small | 9473 |  |  | 5402 US 401K Maintenance Rejection File (MVP1: Rejection File) People Total Rewards | 2019-07-24 | COE Team Discovery | Completed | 2018-06-05 |  |  | Wendy.Byers@walmart.com | Weekly |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 1 | 0 | 1 | 0 |  |  |  |  | HOST, Shared Drive | No |  | 1 |  | 1 |  | 1 | Wendy Byers
5403 | Attended | 40068035 | REC000240 | Data Pull (Indeed.com) | Data scraping of Indeed.com website of job listing | New | 2018-07-19 | 2018-07-30 | 2018-08-17 | Jonathan Shoppach | Pasha Maleknia | Charlene Walker | TR Digital Factory | Production | Yes | US | TR Digital Factory | People | Total Rewards | 3 | 20 |  |  | 9473 | X-Small | 9473 |  |  | 5403 US Data Pull (Indeed.com) People Total Rewards | 2019-07-24 | COE Team Discovery | Completed | 2018-08-20 |  |  | Andrew.Beasley@walmart.com | Ad Hoc |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 0 | 0 | 1 | 0 |  |  |  |  | Website, Shared Drive, Excel | No |  | 1 |  | 1 |  | 1 | Andrew Beasley
5404 | Attended | 40068035 | REC000241 | Data Pull (ERI.com) | Data scraping of Indeed.com website of job listing | New | 2018-07-19 | 2018-07-30 | 2018-08-17 | Jonathan Shoppach | Pasha Maleknia | Charlene Walker | TR Digital Factory | Production | Yes | US | TR Digital Factory | People | Total Rewards | 3 | 20 |  |  | 9473 | X-Small | 9473 |  |  | 5404 US Data Pull (ERI.com) People Total Rewards | 2019-07-24 | COE Team Discovery | Completed | 2018-08-20 |  |  | Andrew.Beasley@walmart.com | Ad Hoc |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 0 | 0 | 1 | 0 |  |  |  |  | Website, Shared Drive, Excel | No |  | 1 |  | 1 |  | 1 | Andrew Beasley
5405 | svcdah16 | 40068035 | REC000242 | Data Pull (BLS) | The Compensation Team will look at the job description and compare against survey sources to determine correct pay rate per region. All job descriptions are then listed in a Master Job list spreadsheet that contains all of the survey sources (ERI, BLS,HAY). The data gathered is then used to create a geographical map of all facilities using Alteryx. | New | 2018-07-19 | 2018-07-30 | 2018-08-17 | Jonathan Shoppach | Andrew Beasley | Charlene Walker | TR Digital Factory | Production | Yes | US | TR Digital Factory | People | Total Rewards | 3 | 20 |  |  | 9473 | X-Small | 9473 |  |  | 5405 US Data Pull (BLS) People Total Rewards | 2019-07-24 | COE Team Discovery | Completed | 2018-08-20 |  |  | Andrew.Beasley@walmart.com | Ad Hoc |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 0 | 0 | 1 | 0 |  |  |  |  | Website, Shared Drive, Excel | No |  | 1 |  | 1 |  | 1 | Andrew Beasley
5406 | svcdah16 | 41679180 | REC000243 | Deferred Comp (Weekly Census) | Weekly Census is run every week to capture terminated officers and sent to 3rd party (New Port). New Port holds deferred account officer information | New | 2018-08-13 | 2019-08-16 | 2019-08-26 | Kaitlin Wolfe | Kelly Trotter | Charlene Walker | TR Digital Factory | Production | Yes | US | TR Digital Factory | People | Total Rewards | 1 | 60 |  |  | 9473 | Small | 9473 |  |  | 5406 US Deferred Comp (Weekly Census) People Total Rewards | 2019-07-24 | COE Team Discovery | Completed | 2018-08-20 |  |  | Kelly.Trotter@walmart.com | Monthly |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 0 | 0 | 1 | 0 |  |  |  |  | HRDW, Excel, Shared Drive | No |  | 1 |  | 1 |  | 1 | Kelly Trotter
5407 | svcdah16 | 41679180 | REC000244 | Deferred Comp (Full Census) | Montly Census is run to capture terminated officers and sent to 3rd party (New Port). New Port holds deferred accounts that are paid out to officers at termination | New | 2018-08-13 | 2019-08-16 | 2019-08-26 | Kaitlin Wolfe | Kelly Trotter | Charlene Walker | TR Digital Factory | Production | No | US | TR Digital Factory | People | Total Rewards |  | 240 |  |  | 9473 | Small | 9473 |  |  | 5407 Deferred Comp (Full Census) People Total Rewards | 2019-07-24 | COE Team Discovery | Completed | [6 empty] | 0 |  |  | 0 |  | 0 | [7 empty] | 0 | [6 empty] | HRDW, Excel, Shared Drive | No |  | 1 |  | 1 |  | 1
5408 | svcdah16 | 41679180 | REC000245 | Deferred Comp (Term Tracking) | Running Report of Termed Officers | New | 2018-08-13 | 2019-08-16 | 2019-08-26 | Kaitlin Wolfe | Kelly Trotter | Charlene Walker | TR Digital Factory | Production | Yes | US | TR Digital Factory | People | Total Rewards | 1 | 30 |  |  | 9473 | Small | 9473 |  |  | 5408 US Deferred Comp (Term Tracking) People Total Rewards | 2019-07-24 | COE Team Discovery | Completed | 2019-09-02 |  |  | Kelly.Trotter@walmart.com | Monthly |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 0 | 0 | 1 | 0 |  |  |  |  | HRDW, Excel, Shared Drive | No |  | 1 |  | 1 |  | 1 | Kelly Trotter
5409 |  |  | REC000246 | Deferred Comp (Distribution) | Process to collect Officer, Name, WIN, payout information and send to NewPort (3rd Party) | New | 2018-08-13 |  | 2018-09-14 | Kaitlin Wolfe | Kelly Trotter | Charlene Walker | TR Digital Factory | Production | No | US | TR Digital Factory | People | Total Rewards |  | 120 |  |  | 9473 | Small | 9473 |  |  | 5409 Deferred Comp (Distribution) People Total Rewards | 2019-07-24 | COE Team Discovery | Completed | [6 empty] | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 0 | 0 | 1 | 0 |  |  |  |  | HRDW, Excel, Shared Drive | No |  | 1 |  | 1 |  | 1
5410 | Attended | 41197917 | REC000247 | Deferred Comp (New Officer Census) | Monthly Census to add New Officers to 3rd party (New Port) registry | New | 2018-08-13 | 2019-08-16 | 2019-08-26 | Kaitlin Wolfe | Kelly Trotter | Charlene Walker | TR Digital Factory | Production | Yes | US | TR Digital Factory | People | Total Rewards | 1 | 30 |  |  | 9473 | Small | 9473 |  |  | 5410 US Deferred Comp (New Officer Census) People Total Rewards | 2019-07-24 | COE Team Discovery | Completed | 2018-08-20 |  |  | Kelly.Trotter@walmart.com | Monthly |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 0 | 0 | 1 | 0 |  |  |  |  | HRDW, Excel, Shared Drive | No |  | 1 |  | 1 |  | 1 | Kelly Trotter
5411 | Attended | 41725017 | REC000248 | SAP Data Extraction (Monthly) | Monthly Extractions of actual spend as part of Budget Forecast | New | 2018-08-13 | 2018-11-12 | 2018-11-29 | Shelby Bardrick | Shelby Bardrick | Charlene Walker | TR Digital Factory | Production | Yes | US | TR Digital Factory | People | Total Rewards | 1 | 60 |  |  | 9473 | Small | 9473 |  |  | 5411 US SAP Data Extraction (Monthly) People Total Rewards | 2019-07-24 | COE Team Discovery | Completed | 2018-12-03 |  |  | Shelby.Bardick@walmart.com | Monthly |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 0 | 0 | 1 | 0 |  |  |  |  | SAP, Excel, Shared Drive | No |  | 1 |  | 1 |  |  | Shelby Bardrick
5412 |  |  | REC000249 | Job Mapping | Compare Survey source job descriptions against Walmart job descriptions | New | 2018-08-13 |  | 2018-09-10 | Kaitlin Wolfe | Kaitlin Wolfe | Charlene Walker | TR Digital Factory | Production | No | US | TR Digital Factory | People | Total Rewards |  |  |  |  | 9473 | Small | 9473 |  |  | 5412 Job Mapping People Total Rewards | 2019-07-24 | COE Team Discovery | Completed |  |  |  | Shelby.Bardick@walmart.com |  |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 0 | 0 | 1 | 0 |  |  |  |  | SAP, Excel, Shared Drive | No |  | 1 |  | 1 |  |  | Shelby Bardrick
5413 | Attended | 40988293 | REC000250 | Total Rewards: Jet.com (Workday) - DOE | Pulling Jet employee deduction and earnings from workday and storing on team's shared site | New | 2018-09-06 | 2018-08-27 | 2018-09-11 | Shelby Bardrick | Margie Molesso | Charlene Walker | TR Digital Factory | Production | Yes | US | TR Digital Factory | People | Total Rewards | 1 | 120 |  |  | 9473 | Small | 9473 |  | Attended Bot | 5413 US Total Rewards: Jet.com (Workday) - DOE People Total Rewards | 2019-07-24 | COE Team Discovery | Completed | 2018-10-01 |  |  | Shelby.Bardick@walmart.com | Daily |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 0 | 0 | 1 | 0 |  |  |  |  | SAP, Excel, Shared Drive | No |  | 1 |  | 1 |  |  | Shelby Bardrick
5415 | Attended | 41725017 | REC000251 | SAP Data Extraction (Daily) | Data Extraction | New | 2018-09-05 | 2018-08-13 | 2018-08-29 | Shelby Bardrick | Shelby Bardrick | Charlene Walker | TR Digital Factory | Production | Yes | US | TR Digital Factory | People | Total Rewards | 5 | 120 |  |  | 9473 | Small | 9473 |  |  | 5415 US SAP Data Extraction (Daily) People Total Rewards | 2019-07-24 | COE Team Discovery | Completed | 2018-08-20 |  |  | Shelby.Bardick@walmart.com | Weekly |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 0 | 0 | 1 | 0 |  |  |  |  | Website, Shared Drive, Excel | No |  | 1 |  | 1 |  |  | Shelby Bardrick
5416 | Attended | 40988293 | REC000252 | Total Rewards: Jet.com- Commuter | Pulling Jet employee Commuter (metro card) from workday and storing on Benefit Accounting Team's shared site | New | 2018-08-13 | 2018-08-27 | 2018-09-11 | Shelby Bardrick | Shelby Bardrick | Charlene Walker | TR Digital Factory | Production | Yes | US | TR Digital Factory | People | Total Rewards | 5 | 30 |  |  | 9473 | Small | 9473 |  |  | 5416 US Total Rewards: Jet.com- Commuter People Total Rewards | 2019-07-24 | COE Team Discovery | Completed | 2018-09-10 |  |  | Shelby.Bardick@walmart.com | Weekly |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 0 | 0 | 1 | 0 |  |  |  |  | Website, Shared Drive, Excel | No |  | 1 |  | 1 |  |  | Shelby Bardrick
5417 | Attended | 40988293 | REC000253 | Total Rewards: Jet.com (Workday) HSA | Pulling Jet employee HSA deductions from workday and storing on Benefit Accounting Team's shared site | New | 2018-08-13 | 2018-08-27 | 2018-09-11 | Shelby Bardrick | Shelby Bardrick | Charlene Walker | TR Digital Factory | Production | Yes | US | TR Digital Factory | People | Total Rewards | 5 | 30 |  |  | 9473 | Small | 9473 |  |  | 5417 US Total Rewards: Jet.com (Workday) HSA People Total Rewards | 2019-07-24 | COE Team Discovery | Completed | 2018-09-10 |  |  | Shelby.Bardick@walmart.com | Monthly |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 0 | 0 | 1 | 0 |  |  |  |  | Website, Shared Drive, Excel | No |  | 1 |  | 1 |  |  | Shelby Bardrick
5418 | Attended | 41725017 | REC000254 | Total Rewards:SAP Monthly Insurance Process | SAP Pull of 6 reports | New | 2018-10-10 | 2018-09-24 | 2018-10-10 | Shelby Bardrick | Shelby Bardrick | Charlene Walker | TR Digital Factory | Production | Yes | US | TR Digital Factory | People | Total Rewards | 5 | 30 |  |  | 9473 | Small | 9473 |  |  | 5418 US Total Rewards:SAP Monthly Insurance Process People Total Rewards | 2019-07-24 | COE Team Discovery | Completed | 2018-10-15 |  |  | Shelby.Bardick@walmart.com | Monthly |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 0 | 0 | 1 | 0 |  |  |  |  | SAP, Excel, Shared Drive | No |  | 1 |  | 1 |  |  | Shelby Bardrick
5419 | Attended | 36239813 | REC000255 | 401K Audit: Distribution Testing (MVP1: Merrill Lynch) | Audit Process | New | 2018-09-27 | 2018-08-13 | 2018-08-29 | Wendy Byers | Wendy Byers | Charlene Walker | TR Digital Factory | Production | Yes | US | TR Digital Factory | People | Total Rewards | 200 | 120 |  |  | 9473 | Small | 9473 |  |  | 5419 US 401K Audit: Distribution Testing (MVP1: Merrill Lynch) People Total Rewards | 2019-07-24 | COE Team Discovery | Completed | 2018-09-10 |  |  | Wendy.Byers@walmart.com | Quarterly |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 0 | 0 | 1 | 0 |  |  |  |  | Merrill Lynch, Excel, Shared Drive | No |  | 1 |  | 1 |  |  | John Doyle
5420 | Attended | 36239813 | REC000256 | 401K Audit: Distribution Testing (MVP2: CSS) | Audit Process | New | 2018-09-27 | 2018-08-13 | 2018-08-30 | Wendy Byers | Wendy Byers | Charlene Walker | TR Digital Factory | Production | Yes | US | TR Digital Factory | People | Total Rewards | 200 | 120 |  |  | 9473 | Small | 9473 |  |  | 5420 US 401K Audit: Distribution Testing (MVP2: CSS) People Total Rewards | 2019-07-24 | COE Team Discovery | Completed | 2018-09-10 |  |  | Wendy.Byers@walmart.com | Quarterly |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 0 | 0 | 1 | 0 |  |  |  |  | CSS, Excel, Shared Drive | No |  | 1 |  | 1 |  |  | John Doyle
5421 | Attended | 41197917 | REC000257 | 401K Maintenance Rejection File(MVP2: ALL) | Process Rejection Files returned by Merrill Lynch | New | 2018-08-06 | 2018-08-13 | 2018-08-29 | Wendy Byers | Wendy Byers | Charlene Walker | TR Digital Factory | Production | Yes | US | TR Digital Factory | People | Total Rewards | 250 | 120 |  |  | 9473 | Small | 9473 |  |  | 5421 US 401K Maintenance Rejection File(MVP2: ALL) People Total Rewards | 2019-07-24 | COE Team Discovery | Completed | 2018-09-17 |  |  | Wendy.Byers@walmart.com | Weekly |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 0 | 0 | 1 | 0 |  |  |  |  | HOST, Excel, Shared Drive | No |  | 1 |  | 1 |  |  | Wendy Byers
5422 |  |  | REC000258 | DOE Recon/Billing Report | Reconciliation of Deduction of Earnings Report | New | 2018-10-03 |  |  | Brian Morrison | Wendy Byers | Charlene Walker | TR Digital Factory | On Hold - Funding | No | US | TR Digital Factory | People | Total Rewards |  |  |  |  | 9473 | Small | 9473 |  |  | 5422 DOE Recon/Billing Report People Total Rewards | 2019-07-24 | COE Team Discovery | Completed | [6 empty] | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 0 | 0 | 1 | 0 | [5 empty] | No |  | 1 |  | 1
5423 |  |  | REC000259 | Refresh of Internal Headcount data | Pay Period End (PPE) Based Data Uploads - Upload headcount, pay and benefit enrollment files to Rock Solid Retail from Walmart and Jet.com. approx 20 files. Level of Effort from business: 1 resource 26/hrs annually. Note: It's a small LOE however there is only 1 resource who know how to perform the work so there is a risk with a single point of failure. | New | 2018-12-10 |  |  | Sebastian Pittaro | Lloyd Walker | Charlene Walker | TR Digital Factory | On Hold - Funding | No | US | TR Digital Factory | People | Total Rewards |  |  |  |  | 9473 | Small | 9473 |  |  | 5423 Refresh of Internal Headcount data People Total Rewards | 2019-07-24 | COE Team Discovery | Completed | [6 empty] | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 0 | 0 | 1 | 0 | [5 empty] | No |  | 1 |  | 1
5424 |  |  | REC000260 | Wire process - Rhode Island Wire | end to end automation of the Wire process | New | 2018-10-19 |  |  | Wendy Byers | Wendy Byers | Charlene Walker | TR Digital Factory | On Hold - Funding | No | US | TR Digital Factory | People | Total Rewards |  |  |  |  | 9473 | Small | 9473 |  |  | 5424 Wire process - Rhode Island Wire People Total Rewards | 2019-07-24 | COE Team Discovery | Completed | [6 empty] | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 0 | 0 | 1 | 0 | [5 empty] | No |  | 1 |  | 1
5425 |  |  | REC000261 | Jet (Workday): Deferred Comp | Pulling Jet employee info from workday | New | 2018-09-27 |  |  | Kelly Trotter | Kelly Trotter | Charlene Walker | TR Digital Factory | On Hold - Funding | No | US | TR Digital Factory | People | Total Rewards |  |  |  |  | 9473 | Small | 9473 |  |  | 5425 Jet (Workday): Deferred Comp People Total Rewards | 2019-07-24 | COE Team Discovery | Completed | [6 empty] | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 0 | 0 | 1 | 0 | [5 empty] | No |  | 1 |  | 1
5426 | svc_dah0028 | 42040320 | REC000262 | Associate Job Reassignment (Hourly) | Associate reassignment within store, radius, and associate preference | New | 2018-08-23 | 2018-03-12 | 2028-03-26 | Herman Vargas | Herman Vargas | Charlene Walker | TR Digital Factory | UAT | Yes | US | TR Digital Factory | People | Total Rewards | 7 | 10 |  |  | 9473 | Medium | 9473 |  |  | 5426 Associate Job Reassignment (Hourly) People Total Rewards | 2019-07-24 | COE Team Discovery | Completed | 2019-04-09 |  |  | Kirk.Hancock@walmart.com | Daily |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 0 | 0 | 1 | 0 |  |  |  |  | Juris, Career Preference, Excel, Shared Drive | No |  | 1 |  | 1 |  |  | Kirk Hancock
5427 |  |  | REC000263 | Jet (Workday): 401K | Pull Jet employee info from workday | New | 2018-09-27 |  |  | Wendy Byers | Herman Vargas | Charlene Walker |  | On Hold - Funding | No | US | TR Digital Factory | People | Total Rewards |  |  |  | 26 hours/year |  | Medium |  |  |  | 5427 Jet (Workday): 401K People Total Rewards | 2019-07-24 | COE Team Discovery | Completed | [6 empty] | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 0 | 0 | 1 | 0 | [5 empty] | No |  | 1 |  | 1
5428 |  |  | REC000264 | Associates final incentive statement PDF file | AsEach year, the Audit team requests final incentive statement screenshots for a small sample of associates for the Incentive Administration team. We use "export to PDF" functionality on field and home office final statements screen to manually provide the PDF files for the last couple years. Incentive administration team would like the automation team to create an attended bot that could retrieve a sample of associates final incentive statement PDF files that are requested by Audit team and place them in an Audit folder for Audit review. If possible set up the bot so Audit could run it without needing to engage Incentive Admin team.sociates final incentive statement PDF file | New | 2018-11-01 |  |  |  | Laura Robey | Charlene Walker |  | On Hold - Funding | No | US | TR Digital Factory | People | Total Rewards |  |  |  | 10 hours/year |  | Medium |  |  |  | 5428 Associates final incentive statement PDF file People Total Rewards | 2019-07-24 | COE Team Discovery | Completed | [6 empty] | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 0 | 0 | 1 | 0 | [5 empty] | No |  | 1 |  | 1
5429 |  |  | REC000265 | Pay Period End (PPE) Based Data Uploads |  | New | 2019-01-30 |  |  |  |  | Charlene Walker |  | On Hold - Funding | No | US | TR Digital Factory | People | Total Rewards | [5 empty] | Medium |  |  |  | 5429 Pay Period End (PPE) Based Data Uploads People Total Rewards | 2019-07-24 | COE Team Discovery | Completed | [6 empty] | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 0 | 0 | 1 | 0 | [5 empty] | No |  | 1 |  | 1
5430 |  |  | REC000266 | Monthly Financial process | TRIO team performing process projecting costs on the plan | New | 2019-01-30 |  |  |  |  | Charlene Walker |  | On Hold - Funding | No | US | TR Digital Factory | People | Total Rewards | [5 empty] | Medium |  |  |  | 5430 Monthly Financial process People Total Rewards | 2019-07-24 | COE Team Discovery | Completed | [6 empty] | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 0 | 0 | 1 | 0 | [5 empty] | No |  | 1 |  | 1
5431 |  |  | REC000267 | IAM - Lincoln LTD and Stat Bi-weekly Itemization |  | New | 2019-01-30 |  |  |  |  | Charlene Walker |  | On Hold - Funding | No | US | TR Digital Factory | People | Total Rewards | [5 empty] | Medium |  |  |  | 5431 IAM - Lincoln LTD and Stat Bi-weekly Itemization People Total Rewards | 2019-07-24 | COE Team Discovery | Completed | [6 empty] | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 0 | 0 | 1 | 0 | [5 empty] | No |  | 1 |  | 1
5431 |  |  | REC000268 | Management Incentive Process | Review end to end processes and steps for MIP | New | 2018-12-10 |  |  | Kandi Kelley | Kandi Kelley | Charlene Walker |  | On Hold - Funding | No | US | TR Digital Factory | People | Total Rewards | [5 empty] | Medium |  |  |  | 5431 Management Incentive Process People Total Rewards | 2019-07-24 | COE Team Discovery | Completed | [6 empty] | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 0 | 0 | 1 | 0 | [5 empty] | No |  | 1 |  | 1
5432 |  |  | REC000269 | LAG Reconciliation Report: Monthly Financial Process: | LAG RECONCILIATION Report: Spreadsheets in different formats coming from different carries making payments to Walmart for Medical Claims, Wellness, etc. used by Walmart to know how much was paid by Walmart and how much did the carrier pay walmart . Level of Effort from business: 1 resource 48hrs/annually | New | 2018-12-10 |  |  |  | Casey Koenigseder | Charlene Walker |  | On Hold - Funding | No | US | TR Digital Factory | People | Total Rewards | [5 empty] | Medium |  |  |  | 5432 LAG Reconciliation Report: Monthly Financial Process: People Total Rewards | 2019-07-24 | COE Team Discovery | Completed | [6 empty] | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 0 | 0 | 1 | 0 | [5 empty] | No |  | 1 |  | 1
5433 |  |  | REC000270 | Budget Allocation: Monthly Financial Process | Actual payments to vendors keyed in by Financial Compliance team (Shelby Bardrick's team) then sent to TRIO team to identify variances. Level of Effort from business: 1 resource 720 hrs/annually | New | 2018-12-10 |  |  |  | Casey Koenigseder | Charlene Walker |  | On Hold - Funding | No | US | TR Digital Factory | People | Total Rewards | [5 empty] | Medium |  |  |  | 5433 Budget Allocation: Monthly Financial Process People Total Rewards | 2019-07-24 | COE Team Discovery | Completed | [6 empty] | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 0 | 0 | 1 | 0 | [5 empty] | No |  | 1 |  | 1
5434 |  |  | REC000271 | Total Rewards:(Migration of Bots) 401K Participant Data | Migration of "Attended" Bot to "Unattended" for 401K Participant Data | New | 2019-02-07 | 2019-02-07 | 2019-02-07 | Kaitlin Wolfe | Wendy Byers | Charlene Walker |  | On Hold - Funding | Yes | US | TR Digital Factory | People | Total Rewards | [5 empty] | Medium |  |  |  | 5434 Total Rewards:(Migration of Bots) 401K Participant Data People Total Rewards | 2019-07-24 | COE Team Discovery | Completed | [6 empty] | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 0 | 0 | 1 | 0 | [5 empty] | No |  | 1 |  | 1
5435 |  |  | REC000272 | Total Rewards: (Migration of Bots) 401K Distribution Testing | Migration of "Attended" Bot to "Unattended" for 401K Distribution Testing | New | 2019-02-07 | 2019-02-07 | 2019-02-07 | Kaitlin Wolfe | Wendy Byers | Charlene Walker |  | On Hold - Funding | Yes | US | TR Digital Factory | People | Total Rewards | [5 empty] | Medium |  |  |  | 5435 Total Rewards: (Migration of Bots) 401K Distribution Testing People Total Rewards | 2019-07-24 | COE Team Discovery | Completed | [6 empty] | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 0 | 0 | 1 | 0 | [5 empty] | No |  | 1 |  | 1
5436 |  |  | REC000273 | Total Rewards: (Migration of Bots): SAP Pull of Daily, Monthly AND Company Insurance | Migration of "Attended" Bot to "Unattended" for SAP Pull of Daily, Monthly, AND Company Insurance | New | 2019-02-07 | 2019-02-07 | 2019-02-07 | Kaitlin Wolfe | Shelby Bardrick | Charlene Walker |  | On Hold - Funding | Yes | US | TR Digital Factory | People | Total Rewards | [5 empty] | Medium |  |  |  | 5436 Total Rewards: (Migration of Bots): SAP Pull of Daily, Monthly AND Company Insurance People Total Rewards | 2019-07-24 | COE Team Discovery | Completed | [6 empty] | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 0 | 0 | 1 | 0 | [5 empty] | No |  | 1 |  | 1
5437 |  |  | REC000274 | Total Rewards: (Migration of Bots): 401K Maintenance (All) | Migration of Bots from Attended to Unattended | New | 2019-02-07 | 2019-02-07 | 2019-02-07 | Kaitlin Wolfe | Shelby Bardrick | Charlene Walker |  | On Hold - Funding | Yes | US | TR Digital Factory | People | Total Rewards | [5 empty] | Medium |  |  |  | 5437 Total Rewards: (Migration of Bots): 401K Maintenance (All) People Total Rewards | 2019-07-24 | COE Team Discovery | Completed | [6 empty] | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 0 | 0 | 1 | 0 | [5 empty] | No |  | 1 |  | 1
5438 |  |  | REC000275 | Total Rewards: (Migration of Bots): Deferred Comp (Weekly, Term Tracking, New Officer) | Migration of Bots from Attended to Unattended | New | 2019-02-07 | 2019-02-07 | 2019-02-07 | Kaitlin Wolfe | Shelby Bardrick | Charlene Walker |  | On Hold - Funding | Yes | US | TR Digital Factory | People | Total Rewards | [5 empty] | Medium |  |  |  | 5438 Total Rewards: (Migration of Bots): Deferred Comp (Weekly, Term Tracking, New Officer) People Total Rewards | 2019-07-24 | COE Team Discovery | Completed | [6 empty] | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 0 | 0 | 1 | 0 | [5 empty] | No |  | 1 |  | 1
5439 |  |  | REC000276 | Total Rewards: (Migration of Bots): Jet.com (Workday) | Migration of Bots from Attended to Unattended | New | 2019-02-07 | 2019-02-07 | 2019-02-07 | Kaitlin Wolfe | Shelby Bardrick | Charlene Walker |  | On Hold - Funding | Yes | US | TR Digital Factory | People | Total Rewards | [5 empty] | Medium |  |  |  | 5439 Total Rewards: (Migration of Bots): Jet.com (Workday) People Total Rewards | 2019-07-24 | COE Team Discovery | Completed | [6 empty] | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 0 | 0 | 1 | 0 | [5 empty] | No |  | 1 |  | 1
5440 |  |  | REC000277 | Total Rewards: (Migration of Bots): Survey Pull ERI, BLS, Hay, Indeed | Migration of Bots from Attended to Unattended | New | 2019-02-07 | 2019-02-07 | 2019-02-07 | Kaitlin Wolfe | Shelby Bardrick | Charlene Walker |  | On Hold - Funding | Yes | US | TR Digital Factory | People | Total Rewards | [5 empty] | Medium |  |  |  | 5440 Total Rewards: (Migration of Bots): Survey Pull ERI, BLS, Hay, Indeed People Total Rewards | 2019-07-24 | COE Team Discovery | Completed | [6 empty] | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 0 | 0 | 1 | 0 | [5 empty] | No |  | 1 |  | 1
8800 |  |  | REC000435 | CMI TLE Claim | Extract information from a TLE document and type into a note in ClaimZone for the corresponding claim | New | 2018-11-01 |  | 2019-02-22 | Todd Joy | Joshua Ray | Charlene Walker |  | On Hold - Funding | No | US | Fixed Capacity | CMI | Claims | 400 | 10 |  | 2200 |  | Medium |  |  |  | 8800 CMI TLE Claim CMI Claims | 2019-07-24 | COE Team Discovery | Completed | [6 empty] | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 0 | 0 | 1 | 0 | [5 empty] | No |  | 1 |  | 1
8801 |  |  | REC000436 | Product Process |  | New | 2018-11-01 |  |  | Todd Joy | Bryce Miracle | Charlene Walker |  | On Hold - Funding | No | US | Fixed Capacity | CMI | Claims |  |  |  | 4000 |  | Medium |  |  |  | 8801 Product Process CMI Claims | 2019-07-24 | COE Team Discovery | Completed | [6 empty] | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 0 | 0 | 1 | 0 | [5 empty] | No |  | 1 |  | 1
8802 |  |  | REC000437 | Garage Keeper Status Update | Check each open claim on a nightly basis to ensure that if the Liability Assessment Field is updated. If updated, automation will follow a set of rules to update the Decision Date and Loss Type Code | New | 2018-11-01 |  |  | Todd Joy | Joshua Ray | Charlene Walker | TR Digital Factory | On Hold - Business Partner | No | US | Fixed Capacity | CMI | Claims | [5 empty] | Medium |  |  |  | 8802 Garage Keeper Status Update CMI Claims | 2019-07-24 | COE Team Discovery | Completed | [6 empty] | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 0 | 0 | 1 | 0 | [5 empty] | No |  | 1 |  | 1
9501 | svc_dad0001 | 42030901 | REC000497 | SRCR Automation (Intake) | The Security Risk and Compliance Review (SRCR) process is a streamlined IT Governance process designed to enable secure deployments of system functions, features and services. A Security Risk and Compliance Review (SRCR) must be completed for all computing systems including, but not limited to software, hardware, voice and data, and network infrastructure equipment running on any platform whether it is to be installed internally or hosted offsite. All existing solutions, systems or infrastructure require a SRCR whenever a material functionality change, update, or upgrade is made to the solution, system, or infrastructure, or if required by Information Security | New | 2019-03-13 | 2019-03-13 | 2019-03-27 | John Pearson | Jamie Holt | Charlene Walker | Big Bots | Development | No | US | Fixed Capacity | Info Sec | Cybersecurity | 25 | 10 |  |  |  | Medium |  |  |  |  | 2019-07-24 | COE Team Discovery | Completed | 2019-04-08 |  |  | John.Pearson@walmart.com | Daily |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 1 | 1 | 0 | 0 | 1 | 0 |  |  |  |  | Arhcer, Excel, | No |  | 1 |  | 1 |  |  | John Pearson
Note on A1: Alex Czechowski: IA360: Process ID Validation: 4-digit number
Note on E1: Alex Czechowski: IA 360: Process Name Validation: any text
Note on F1: Alex Czechowski: IA 360: Description Validation: any text
Note on G1: Alex Czechowski: IA 360: Development Type Validation: New OR Enhancement

## Chao Upload
Process ID | Bot ID | SRCR # | Record ID | Process Name | Description | Type | Request Date | Discovery Start Date | Ready for Scrum Date | Requester | Process Owner | Product Manager | Dev Team | Current Status | Funding | Country | Initiative | Domain | Product Area | # of transactions | Associate avg time (mins) | ROI | Number of FTE | Est. Budget | T shirt size | Actual Budget | Tenant Name | Comments | Name | Last Updated Date | Service Type | Request Status | Development Start Date | Go Live Date | Decommissioned Date | Process Owner Email | Process Frequency | Cost of One Full Time Associate | Expense Reduction | Expense Reduction Dollar Amount | Expense Reduction Frequency | Headcount Reduction | Headcount Reduction Amount (estimate) | Revenue Generated | Revenue Generated Dollar Amount | Revenue Generated Frequency | Cost Avoidance | Cost Avoidance Dollar Amount | Hours Saved | Error Reduction | Volume | Compliance | Associate/Customer Experience | Expanded Services | Cost Center Area Name | Cost Center Number | Dollar Amount Charged | Production Machine(s) | Applications | SOX | CRQ Number | Design Review Approved | Design Review Approved By | Code Review Approved | Code Review Approved By | Business Approval | Business Approval By
6013 |  |  | REC000361 | Close PO/Open Commitment | We currently have an FTE working this process today and we would like to automate the process. This would be closing out open POs that have outstanding finds available and not invoiced for a set period of time. This process will return budget back to the business areas, as well as reduction of FTE costs. That value is still TBD. | New | 2019-01-01 |  |  | Sue Orourke |  | Chaoying Yan |  | New | Yes | US | IPS | IPS | Operational Procurement | [9 empty] | 6013 Close PO/Open Commitment IPS Operational Procurement | 2019-07-24 | COE Team Discovery | Completed | [16 empty] | 1 | 1 |  |  | 1
6052 |  |  | REC000402 | Pull Traits |  | New | 2019-06-18 |  |  | Donna Feyen | Tiffany Williams | Chaoying Yan |  | New | No, but can secure | US | IPS | IPS | Procurement Services |  | 60 |  |  |  | Small |  |  |  |  | 2019-07-24 | COE Team Discovery | Completed | [16 empty] | 1 | 1 |  |  | 1
6054 |  |  | REC000404 | Reconcile/Remedy Warehouse Out Errors |  | New | 2019-06-18 |  |  | Donna Feyen |  | Chaoying Yan |  | New | No, but can secure | US | IPS | IPS | Procurement Services | [10 empty] | 2019-07-24 | COE Team Discovery | Completed | [16 empty] | 1 | 1 |  |  | 1
6055 |  |  | REC000405 | Reconcile/Remedy Add-On Order Errors |  | New | 2019-06-18 |  |  | Donna Feyen |  | Chaoying Yan |  | New | No, but can secure | US | IPS | IPS | Procurement Services | [10 empty] | 2019-07-24 | COE Team Discovery | Completed | [16 empty] | 1 | 1 |  |  | 1
6056 |  |  | REC000406 | Storage Trailers release PO |  | New | 2019-06-18 |  |  | Donna Feyen |  | Chaoying Yan |  | New | No, but can secure | US | IPS | IPS | Procurement Services | [10 empty] | 2019-07-24 | COE Team Discovery | Completed | [16 empty] | 1 | 1 |  |  | 1
6057 |  |  | REC000407 | R Blocking Releasing | Work on the R-Block item on the Mannul tab | New | 2019-06-17 | 2019-07-03 |  | Donna Feyen | Debbie Hopkins | Chaoying Yan | GTS-IPS | In Discovery | Yes | US | IPS | IPS | AP GNFR | 96 | 10 | 24960 |  |  | Medium |  |  |  |  | 2019-07-24 | COE Team Discovery | Completed | [9 empty] | 0 | [6 empty] | 1 | 1 |  |  | 1 | [5 empty] | SAP, Excel, Outlook
6037 |  |  | REC000387 | Assigning Loading Preferred Vendor | Assigning and loading preferred vendors | New | 2019-04-23 | 2019-04-23 |  | Donna Feyen | Stacey Sykes, Karen Corshia | Chaoying Yan |  | On Hold | Yes | US | IPS | IPS | Procurement Services | 10 | 60 | 16800 |  |  | Large |  |  |  |  | 2019-07-24 | COE Team Discovery | Completed | [26 empty] | Outlook, ShareDrive, Excel, Quickbase, Access
6058 |  |  | REC000408 | PO creation for Construction Projects | PO Creation process for the Procurement Team, this process is for new store/remodel construction/special project construction/HVAC/Refrigeration Capex | New | 2019-06-25 | 2019-06-26 |  | Donna Feyen | Whitney Riley, Nancy Burton | Chaoying Yan | Bot Heroes | In Discovery | Yes | US | IPS | IPS | Procurement Services | 1000 | 15 | 280800 | 6 |  | Medium |  |  |  |  | 2019-07-24 | COE Team Discovery | Completed | [9 empty] | 1 | 6 | [5 empty] | 1 | 1 |  |  | 1 | [5 empty] | Outlook, Pulse, ShareDrive, SAP
6059 |  |  | REC000409 | PO creation for FM Equip & Parts | PO Creation process for the Procurement Team, this process is for FM Equipment and Parts | New | 2019-06-25 | 2019-07-10 |  | Donna Feyen | Shannon Gautney, Susan Kissinger | Chaoying Yan | Bot Heroes | In Discovery | Yes | US | IPS | IPS | Procurement Services |  |  | 93600 | 2 |  | Medium |  |  |  |  | 2019-07-24 | COE Team Discovery | Completed | [9 empty] | 1 | 2 | [5 empty] | 1 | 1 |  |  | 1
6009 |  |  | REC000357 | Ariba Buy-IT for Canada Supplier Enablement (MDM) | A Net Supplier or Existing Supplier who are new to the Ariba Network need to be added to the Vendor Table in ECC with the ACMID and ANID from Ariba | New | 2018-12-17 | 2019-01-09 | 2019-02-01 | Sue Orourke | Adam Martin | Chaoying Yan | GTS-IPS | In UAT | Yes | CA | IPS | IPS | Operational Procurement | 5 | 30 | 46800 |  |  | Small |  |  |  | 6009 Ariba Buy-IT for Canada Supplier Enablement (MDM) IPS Operational Procurement | 2019-07-24 | COE Team Discovery | Completed | [9 empty] | 0 | [6 empty] | 1 | 1 |  |  | 1 | [5 empty] | Ariba, SAP, SharePoint
6016 |  |  | REC000364 | Quick Sourcing (Tactical) | A Sourcing Request needs to be processed and information needs to be manually populated. Sourcing project needs to be manually created from Sourcing Request in Ariba. | New | 2019-01-01 |  |  | Sue Orourke |  | Chaoying Yan |  | Cancelled | No | CA | IPS | IPS | Ariba BuyIt | [9 empty] | 6016 Quick Sourcing (Tactical) IPS Ariba BuyIt | 2019-07-24 | COE Team Discovery | Completed
6017 |  |  | REC000365 | Transmit Purchase Order | User needs to send the PO to Non-AN supplier manually and change the PO status from ordering to Ordered. | New | 2019-01-01 |  |  | Sue Orourke |  | Chaoying Yan |  | Cancelled | No | CA | IPS | IPS | Ariba BuyIt | [9 empty] | 6017 Transmit Purchase Order IPS Ariba BuyIt | 2019-07-24 | COE Team Discovery | Completed
6018 |  |  | REC000366 | TPI Vendor Identification | Proposed process and solution is have MDM team update ECC table with every TPI change daily | New | 2019-01-01 |  |  | Sue Orourke |  | Chaoying Yan |  | Cancelled | No | CA | IPS | IPS | Ariba BuyIt | [9 empty] | 6018 TPI Vendor Identification IPS Ariba BuyIt | 2019-07-24 | COE Team Discovery | Completed
6019 |  |  | REC000367 | Non-Catalog Triage | A free-text request is sent by enhanced users and Operational Procurement first checks if item is already included in catalog. A bot could do the same search and approve/deny PR | New | 2019-01-01 |  |  | Sue Orourke |  | Chaoying Yan |  | Cancelled | No | CA | IPS | IPS | Ariba BuyIt | [9 empty] | 6019 Non-Catalog Triage IPS Ariba BuyIt | 2019-07-24 | COE Team Discovery | Completed
6020 |  |  | REC000368 | Scanning | Invoices received by Suppliers can be dropped in a central repository. These invoices need to be scanned manually. | New | 2019-01-01 |  |  | Sue Orourke |  | Chaoying Yan |  | Cancelled | No | CA | IPS | IPS | Ariba BuyIt | [9 empty] | 6020 Scanning IPS Ariba BuyIt | 2019-07-24 | COE Team Discovery | Completed
6021 |  |  | REC000369 | Indexing | Scanned image of the invoice needs to be manually indexed for entering invoices in system. | New | 2019-01-01 |  |  | Sue Orourke |  | Chaoying Yan |  | Cancelled | No | CA | IPS | IPS | Ariba BuyIt | [9 empty] | 6021 Indexing IPS Ariba BuyIt | 2019-07-24 | COE Team Discovery | Completed
6022 |  |  | REC000370 | Invoice Submission | Invoices received from Non-AN Supplier need to entered manually in Ariba P2P system. | New | 2019-01-01 |  |  | Sue Orourke |  | Chaoying Yan |  | Cancelled | No | CA | IPS | IPS | Ariba BuyIt | [9 empty] | 6022 Invoice Submission IPS Ariba BuyIt | 2019-07-24 | COE Team Discovery | Completed
6023 |  |  | REC000371 | Invoice Submission in SAP | SAP Invoices need to be posted manually taking reference of the Non-Electronic Supplier Invoices | New | 2019-01-01 |  |  | Sue Orourke |  | Chaoying Yan |  | Cancelled | No | CA | IPS | IPS | Ariba BuyIt | [9 empty] | 6023 Invoice Submission in SAP IPS Ariba BuyIt | 2019-07-24 | COE Team Discovery | Completed
6024 |  |  | REC000372 | Invoice Validation | Comparison of electronic invoice and Hard copy received from Supplier is a manual process. | New | 2019-01-01 |  |  | Sue Orourke |  | Chaoying Yan |  | Cancelled | No | CA | IPS | IPS | Ariba BuyIt | [9 empty] | 6024 Invoice Validation IPS Ariba BuyIt | 2019-07-24 | COE Team Discovery | Completed
6025 |  |  | REC000373 | NCS Processing (Purchase Req. Creation) | Auto creation of PR from invoice for After the Fact invoice against a NCS spend for a non catalog material | New | 2019-01-01 |  |  | Sue Orourke |  | Chaoying Yan |  | Cancelled | No | CA | IPS | IPS | Ariba BuyIt | [9 empty] | 6025 NCS Processing (Purchase Req. Creation) IPS Ariba BuyIt | 2019-07-24 | COE Team Discovery | Completed
6026 |  |  | REC000374 | Contract Management | Contract Deconstruction | New | 2019-01-01 |  |  | Sue Orourke |  | Chaoying Yan |  | Cancelled | No | CA | IPS | IPS | Ariba BuyIt | [9 empty] | 6026 Contract Management IPS Ariba BuyIt | 2019-07-24 | COE Team Discovery | Completed
6031 |  |  | REC000379 | Supplier Enablement |  | New | 2019-03-11 |  |  | Nick Antao |  | Chaoying Yan |  | Cancelled | No | CA | IPS | IPS | Ariba BuyIt | [10 empty] | 2019-07-24 | COE Team Discovery | Completed
6010 | svcdai0001 |  | REC000358 | Ariba Buy-IT for Canada Price Tracking-Catalog Management | Syncing of price updates between Supplier Managed Catalog items in Ariba Buyit and Article master records in ECC | New | 2018-12-17 |  | 2019-03-18 | Sue Orourke & Dallas Hardison | Jessica Tabares | Chaoying Yan | GTS-IPS | Cancelled | No | CA | IPS | IPS | Operational Procurement | [9 empty] | 6010 Ariba Buy-IT for Canada Price Tracking-Catalog Management IPS Operational Procurement | 2019-07-24 | COE Team Discovery | Completed
6041 |  |  | REC000391 | 382 to SAP |  | New | 2019-04-25 |  |  | Donna Feyen |  | Chaoying Yan |  | Cancelled | No | US | IPS | IPS | Procurement Services | [10 empty] | 2019-07-24 | COE Team Discovery | Completed
6043 |  |  | REC000393 | PPA TIPS | Validate and Process the claim requests come from emails | New | 2019-04-25 |  |  | Donna Feyen | Amanda Kester | Chaoying Yan |  | Cancelled | No | US | IPS | IPS | Procurement Services-PPA |  |  | 154857 | [7 empty] | 2019-07-24 | COE Team Discovery | Completed
6047 | PPA Service Channel HP JDE |  | REC000397 | PPA GNFR | Validate if invoice has been paid twice or wrong amount and file the claim in BPM for AP team to process | New | 2019-05-22 |  |  | Donna Feyen | Amanda Kester | Chaoying Yan |  | Cancelled | No | US | IPS | IPS | Procurement Services-PPA | [10 empty] | 2019-07-24 | COE Team Discovery | Completed
6048 | PPA Service Channel Audit TIPS |  | REC000398 | PPA Journal Entry | User reviews information and validates Company Codes to FI Org spreadsheet prior to upload of JE. | New | 2019-05-22 |  |  | Donna Feyen | Amanda Kester | Chaoying Yan |  | Cancelled | No | US | IPS | IPS | Procurement Services-PPA | [10 empty] | 2019-07-24 | COE Team Discovery | Completed
6033 |  |  | REC000381 | QB Supplier Development App with Automation |  | New | 2019-03-11 |  |  | Donna Feyen |  | Chaoying Yan |  | Cancelled | No | US | IPS | IPS | Real Estate | [10 empty] | 2019-07-24 | COE Team Discovery | Completed
6034 |  |  | REC000382 | Budget Error Process Streamlining and Mass PO and Contract Creation |  | New | 2019-03-11 |  |  | Donna Feyen |  | Chaoying Yan |  | Cancelled | No | US | IPS | IPS | Real Estate | [10 empty] | 2019-07-24 | COE Team Discovery | Completed
6035 |  |  | REC000383 | APP Dev and Future Bot: Certificate of Insurance (COI) and/or Closeout OCR/Bot Potential |  | New | 2019-03-11 |  |  | Donna Feyen |  | Chaoying Yan |  | Cancelled | No | US | IPS | IPS | Real Estate | [10 empty] | 2019-07-24 | COE Team Discovery | Completed
6032 |  |  | REC000380 | Six pending request to be researched |  | New | 2019-03-11 |  |  | Donna Feyen |  | Chaoying Yan |  | Cancelled | No | US | IPS | IPS | Smart Spend | [10 empty] | 2019-07-24 | COE Team Discovery | Completed
6014 |  |  | REC000362 | Indirect Supplier Newsfeed Automation | Daily supplier, category, market intelligence distributed to the GBS organization by subscription | New | 2019-01-01 |  |  | Sue Orourke |  | Chaoying Yan |  | Cancelled | Pending | US | IPS | IPS | Strategic Sourcing | [9 empty] | 6014 Indirect Supplier Newsfeed Automation IPS Strategic Sourcing | 2019-07-24 | COE Team Discovery | Completed
6015 |  |  | REC000363 | Chatbot for Supplier Information | Does not exist today. Internally focused information knowledgebase ; manually researched today; would provide NRT response increasing stakeholder satisfaction | New | 2019-01-01 |  |  | Sue Orourke |  | Chaoying Yan |  | Cancelled | Pending | US | IPS | IPS | Strategic Sourcing | [9 empty] | 6015 Chatbot for Supplier Information IPS Strategic Sourcing | 2019-07-24 | COE Team Discovery | Completed
6038 |  |  | REC000388 | APP Dev and Future Bot: Certificate of Insurance (COI) and/or Closeout OCR/Bot Potential |  | New | 2019-01-02 |  |  | Donna Feyen |  | Chaoying Yan |  | Cancelled | No | US | IPS | IPS | Supplier and Location Services | [10 empty] | 2019-07-24 | COE Team Discovery | Completed
6039 |  |  | REC000389 | Budget Error Process Streamlining and Mass PO and Contract Creation |  | New | 2019-01-03 |  |  | Donna Feyen |  | Chaoying Yan |  | Cancelled | No | US | IPS | IPS | Supplier and Location Services | [10 empty] | 2019-07-24 | COE Team Discovery | Completed
6040 |  |  | REC000390 | Mass PO Creation Bot RPS Distro Pos |  | New | 2019-01-04 |  |  | Donna Feyen |  | Chaoying Yan |  | Cancelled | No | US | IPS | IPS | Supplier and Location Services | [10 empty] | 2019-07-24 | COE Team Discovery | Completed
6036 |  |  | REC000384 | AP GFR BPM to Rapids BPM Enhancement | Get the invoice/dispute/claim information from BPM request, and enter them into Rapids for further processing | Enhancement | 2019-06-20 | 2019-06-26 | 2019-06-28 | Sue Orourke | Maritza Ortiz | Chaoying Yan | Bot Heroes | Development Started | Yes | US, CA | IPS | IPS | AP GNFR | 2250 | 20 | 315000 | 7 |  | X-Small |  |  | 4 FTE Saving and 3 temp cost avoidence |  | 2019-07-24 | COE Team Discovery | Completed | [9 empty] | 1 | [6 empty] | 1 | 1 | 1 |  | 1 | 1 |  |  |  |  | BPM, Rapids, Excel
6036 |  |  | REC000385 | AP GFR BPM to Rapids Operational Report Development | Get the invoice/dispute/claim information from BPM request, and enter them into Rapids for further processing | Enhancement | 2019-06-20 | 2019-05-29 | 2019-05-30 | Sue Orourke | Maritza Ortiz | Chaoying Yan | Bot Heroes | Development Started | Yes | US, CA | IPS | IPS | AP GNFR | 2250 | 20 | 315000 | 7 |  | X-Small |  |  | 4 FTE Saving and 3 temp cost avoidence |  | 2019-07-24 | COE Team Discovery | Completed | [9 empty] | 1 | [6 empty] | 1 | 1 | 1 |  | 1 | 1 |  |  |  |  | BPM, Rapids, Excel
6051 |  |  | REC000401 | R Blocking Reporting | GBS associate pulls a MRBR report from SAP to create the R-Block Report with multiple tabs . Once the report is built by sorting and filtering, the associate sends the report to select business areas to create goods receipts. | New | 2019-06-17 | 2019-06-20 | 2019-06-28 | Donna Feyen | Debbie Hopkins | Chaoying Yan | GTS-IPS | Development Started | Yes | US | IPS | IPS | AP GNFR | 1 | 240 | 6240 |  |  | Small |  |  |  |  | 2019-07-24 | COE Team Discovery | Completed | [9 empty] | 1 | [6 empty] | 1 | 1 |  |  | 1 | [5 empty] | Excel, Outlook, ShareDrive
6042 |  |  | REC000392 | PPA HP JDE | Validate and Process the claim requests come from BPM | New | 2019-04-25 | 2019-05-16 | 2019-06-04 | Donna Feyen | Amanda Kester | Chaoying Yan | GTS-IPS | Development Started | Yes | US | IPS | IPS | Procurement Services-PPA | 5 | 240 | 387143 |  |  | Large |  |  |  |  | 2019-07-24 | COE Team Discovery | Completed | [9 empty] | 0 |  | 1 | 500000 | Annually |  |  | 1 | 1 |  | 1 | 1 | 1 |  |  |  |  | SAP, JDE, Service Channel, BPM, SharePoint
6030 |  |  | REC000378 | NISC Automation | Utility bill validation for Canada store and DC | New | 2019-03-11 | 2019-04-10 | 2019-04-19 | Sue Orourke | Michael McCraw | Chaoying Yan |  | In Production | Yes | CA | IPS | IPS | AP GNFR | 5 | 48 | 6000 |  |  | X-Small |  |  |  |  | 2019-07-24 | Citizen/Federated Development | Completed | [9 empty] | 0 | [6 empty] | 1 | 1 |  |  | 1 | [5 empty] | SAP, Excel
6036 | svcda07, svcda06 |  | REC000386 | AP GFR BPM to Rapids | Get the invoice/dispute/claim information from BPM request, and enter them into Rapids for further processing | New | 2019-03-06 | 2019-03-08 | 2019-03-22 | Sue Orourke | Maritza Ortiz | Chaoying Yan | GTS-IPS | In Production | Yes | US, CA | IPS | IPS | AP GNFR | 2250 | 20 | 315000 | 7 |  | Large |  |  | 4 FTE Saving and 3 temp cost avoidence |  | 2019-07-24 | COE Team Discovery | Completed | [9 empty] | 1 | 7 |  |  |  | 1 | 180000 | 1 | 1 | 1 |  | 1 | [5 empty] | BPM, Rapids, Excel
6008 | svcdai0000 |  | REC000356 | Continuous Business Planning Process Automation | A rolling 365d view to upcoming sourcing opportunities; completely manual today, well documented process, could be easily automated | New | 2018-11-27 | 2018-12-04 | 2018-12-18 | Sue Orourke | Robert Brindle | Chaoying Yan | Nano Bots | In Production | Yes | US | IPS | IPS | Strategic Sourcing | 1 | 1200 | 223262 |  |  | Medium |  |  |  | 6008 US Continuous Business Planning Process Automation IPS Strategic Sourcing | 2019-07-24 | COE Team Discovery | Completed | [9 empty] | 0 | [6 empty] | 1 | 1 |  |  | 1 | [5 empty] | Excel, Outlook
6044 |  |  | REC000394 | Store Cable TV Invoices | Previsioning and managing cable and telecom invoices for stores and DC | New | 2019-05-10 |  |  | Chuck Scott | NA | Chaoying Yan |  | On Hold | No, but can secure | US | IPS | IPS | AP | [10 empty] | 2019-07-24 | COE Team Discovery | Completed
6050 |  |  | REC000400 | Load Scopes on Sharepoint and review projects for item needs | Load Scopes on Sharepoint and review projects for item needs | New | 2019-06-10 |  |  | Donna Feyen | NA | Chaoying Yan |  | On Hold | No, but can secure | US | IPS | IPS | Procurement Services | [10 empty] | 2019-07-24 | COE Team Discovery | Completed
6012 |  |  | REC000360 | Marketing PO Creation | We are in the process of onboarding all of Walmart US Marketing spend into No PO No Pay. The current annual spend for this work is $1.7 Billion. This is currently being done Non-PO, so although there might not be a true ROI, we can capture this as spend under management. There will be some ROI savings in the AP area, as they currently have someone hand keying these invoices manually. If we can automate the PO creation process, we could then leverage e-invoicing against the PO, which will eliminate the need for manual processing of invoices. | New | 2018-12-18 |  |  | Sue Orourke | Brandon Blunt | Chaoying Yan |  | On Hold | No, but can secure | US | IPS | IPS | Operational Procurement | [9 empty] | 6012 Marketing PO Creation IPS Operational Procurement | 2019-07-24 | COE Team Discovery | Completed
6049 |  |  | REC000399 | PO Creation for Energy and Realty | ProcureIT request submitted with need for PO creation | New | 2019-06-10 |  |  | Donna Feyen | Kevin Jayne | Chaoying Yan |  | On Hold | No, but can secure | US | IPS | IPS | Operational Procurement | [10 empty] | 2019-07-24 | COE Team Discovery | Completed
Note on A1: Alex Czechowski: IA360: Process ID Validation: 4-digit number
Note on E1: Alex Czechowski: IA 360: Process Name Validation: any text
Note on F1: Alex Czechowski: IA 360: Description Validation: any text
Note on G1: Alex Czechowski: IA 360: Development Type Validation: New OR Enhancement